## Catalytic Project List sp
ANNEXURE 1: Catalytic Urban Development Programmes List
Project List |  |  |  | Funding Source (Total Project Value) | [9 empty] | Programme Status (% of Project Complete)
[5 empty] | Municipal |  |  |  |  | Private Funding
Metro | Integration Zone | Catalytic Programme | Catalytic Projects | Total Value (R'm) | Own | Loan | Grant | Provincial | SOE | PPP | SPV | Private Sector only | Private Sector Leverage % | Inception | Concept | Pre Feasibility | Feasibility | Preparation Finalisation
CITY OF JOBURG | LOUI BOTHA
|  | Watt street | Watt Street Inter-change New Housing Development WYNBERG E Regional | 4000000 | 2000000 | 2000000 | [7 empty] | 0% | 0% | 0% | 0% | 0%
|  |  | Watt Street Precinct, Wynberg | [10 empty] | 0% | 0% | 0% | 0% | 0%
|  | Patterson park | Paterson Park - stormwater &new social facilities, park and road upgradings | 292412300 | 0 | 90125300 | 202287000 | [6 empty] | 100% | 53% | 40% | 64% | 257%
|  |  | Patterson Park Renewal Park ORANGE GROVE E City Wide | [10 empty] | 100% | 0% | 0% | 0% | 133%
| EMPIRE-PERTH | Milpark precinct
|  |  | Milpark Precinct Implementation | [10 empty] | 50% | 40% | 9% | 33% | 132%
| MINING BELT | Mining Belt West
|  |  | Mining Belt West Development Corridor (Eastern Precinct):Technical studies on expropriation requirements, to release the necessary land to allow for new roads, road realignments and the widening of road reserves. | 13880000 | 12380000 | 1500000 | [7 empty] | 0% | 0% | 0% | 0% | 0%
|  |  | Detailed Road Master Plan for Mining Belt West Development Corridor | 65000000 | 55000000 | 10000000 | [7 empty] | 10% | 0% | 0% | 3% | 13%
Mining Belt East
| TURFFONTEIN | CORR | CORR - Turffontein Corridor of Freedom Traffic Impact Assessment (TIA), Stormwater Masterplan and New Construction and Upgrading Renewal Corridors of Freedom Intervention Renewal Stormwater Management Projects JOHANNESBURG F Regional | [10 empty] | 80% | 50% |  | 43% | 173%
|  |  | Upgrading of Pioneer Park Renewal Park TURFFONTEIN F Regional | [10 empty] | 100% | 80% | 5% | 63% | 248%
|  |  | Turffontein Corridor (Housing) Renewal Corridors of Freedom Intervention TURFFONTEIN F Regional | [14 empty] | 0%
|  |  | Rotunda Park Precinct Turffontein Corridor (JDA) New Precinct Redevelopment TURFFONTEIN F Regional | 3000000 |  | 3000000 | [7 empty] | 100% | 50% |  | 50% | 173%
| SOWETO CORRIDOR | Jabulani Mixed Use Node | Jabulani Precinct Upgrades | [10 empty] | 80% | 40% | 25% | 48% | 193%
|  |  | Jabulani Cultural Precinct | [10 empty] | 90% | 60% | 40% | 63% | 253%
|  |  | Jabulani station Renewal Nodal Transportatio Facilities | [10 empty] | 50% | 15% | 0% | 22% | 87%
|  |  | Jabulani Electrification | [10 empty] | 30% | 10% | 0% | 13% | 53%
|  |  | Soweto Theatre-Building renovations and upgrades JABULANI D | [10 empty] | 90% | 60% | 60% | 70% | 280%
|  |  | Jabulani social housing project region D | 25000000 | 25000000 | 0 | [7 empty] | 50% | 15% | 0% | 22% | 87%
Nancefield Mixed Use Node
| INNER CITY | City deep hub | MOB - City Deep Freight Hub. Renewal Roads: Construction and Upgrades CITY DEEP F City Wide | 30000000 | 20000000 | 10000000 | [11 empty] | 0%
|  | Eastern gate way | Inner City Eastern Gateway_high_density_residential_neighbourhoods_Ellis Park Precinct, Kazerne, Mongololo Informal Settlement | [10 empty] | 20% | 0% | 0% | 8% | 28%
|  |  | Inner City Eastern Gateway_Development Infill in existing neighbourhoods | [10 empty] | 10% | 0% | 0% | 3% | 13%
|  |  | Inner City Eastern Gateway_TOD and Movement Corridors | [10 empty] | 10% | 0% | 0% | 3% | 13%
|  |  | Inner City Eastern Gateway_Parks_Community Facilities_NMT | [10 empty] | 10% | 0% | 0% | 3% | 13%
Note on N4: LisaMay: calculated field

## Catalytic Project List
Project List |  |  | Funding Source (Total Project Value) | [10 empty] | Project Status (% of Project Complete)
Metro | No. of projects reflected on pipeline | Example of Catalytic Projects | Total Value (R'm) | Municipal | Loan | Grant | Province | SOE | PPP | Total | % of Total | % Total Value | Private Sector Leverage (R'm) | Selection | Preparation | Construction | Completed | Total
|  | Inner City Partnership Fund | 45697000 | 5945000 | 39752000 |  |  |  |  | 45697000 | 100% | 100% |  | 50% | 50% | 50% | 50% | 200%
INNER CITY | 22 | Inner City Buildings Acquisitions | 51200000 | 31200000 | 20000000 |  |  |  |  | 51200000 | 100% | 100% |  | 50% | 50% | 50% | 50% | 200%
|  | Inner City Upgrading (Transitional/Emergency and Rental Stock) Renewal Rental Flats JOHANNESBURG F Regional | 13975000 | 0 | 13975000 |  |  |  |  | 13975000 | 100% | 100% |  | 20% | 20% | 20% | 20% | 80%
|  | Large: Public Transport Facility Redevelopment of Karzene, NEWTOWN EXT.1 Region F | 25000000 | 25000000 | [5 empty] | 25000000 | 100% | 100% |  | 100% | 100% | 75% | 38% | 313%
|  | Managed Lanes: Dedicated Public Transport Lanes: Inner City | 20000000 | 20000000 | 0 |  |  |  |  | 20000000 | 100% | 100% |  | 50% | 0% | 0% | 17% | 67%
|  | Neibourhood Development for Bertrams Priority Block New Building Alterations BERTRAMS F Regional | [7 empty] | 0 | 0% | 0% |  | 50% | 40% | 0% | 30% | 120%
|  | Inner City Roadmap Economic Development Initiatives Renewal Inner City Intervention JOHANNESBURG F Regional | 15000000 | 0 | 15000000 |  |  |  |  | 15000000 | 100% | 100% |  | 60% | 30% | 30% | 40% | 160%
|  | Casamia Inner City Building Upgrade Region F | [7 empty] | 0 | 0% | 0% |  | 100% | 80% | 0% | 60% | 240%
|  | Inner City public environment and social facilities to support Affordable Housing strategy for Inner City Renewal | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Inner City Eastern Gateway_high_density_residential_neighbourhoods_Ellis Park Precinct, Kazerne, Mongololo Informal Settlement | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Inner City Eastern Gateway_Development Infill in existing neighbourhoods | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Inner City Eastern Gateway_TOD and Movement Corridors | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Inner City Eastern Gateway_Parks_Community Facilities_NMT | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Large Public Transport Facility: Redevelopment of Jack Mincer and/or, Carr Street, Inner City | 25000000 | 25000000 | [5 empty] | 25000000 | 100% | 100% |  | 0% | 0% | 0% | 0% | 0%
|  | Hillbrow Tower Precinct | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Innercity Core PEU (Including the Southern Parts) | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Park Station to Civic Centre PEU (Park Station Regeneration) | 37000000 | 20000000 | 17000000 |  |  |  |  | 37000000 | 100% | 100% |  | 100% | 10% | 0% | 37% | 147%
|  | Innercity Eastern Gateway | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Fordsburg PEU | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Ghandi Square East | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Mayfair PEU | 40000000 | 0 | 40000000 |  |  |  |  | 40000000 | 100% | 100% |  | 50% | 0% | 0% | 17% | 67%
|  | 80 Plein Street Inner City Building Conversion Region F | 31000000 | 31000000 | [5 empty] | 31000000 | 100% | 100% | [5 empty] | 0%
JABULANI | 6 | Jabulani Precinct Upgrades | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Jabulani Cultural Precinct | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Jabulani social housing project region D | 25000000 | 25000000 | 0 |  |  |  |  | 25000000 | 100% | 100% |  | 50% | 15% | 0% | 22% | 87%
|  | Jabulani station Renewal Nodal Transportatio Facilities | 35500000 | 3500000 | 32000000 |  |  |  |  | 35500000 | 100% | 100% |  | 40% | 40% | 20% | 33% | 133%
|  | Soweto Theatre-Building renovations and upgrades JABULANI D | 2840497 | 0 | 2840497 |  |  |  |  | 2840497 | 100% | 100% |  | 90% | 60% | 60% | 70% | 280%
|  | Jabulani Electrification | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
LOUIS BOTHA | 8 | Watt Street Precinct, Wynberg | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Paterson Park - stormwater &new social facilities, park and road upgradings | 292412300 | 0 | 90125300 | 202287000 |  |  |  | 292412300 | 0% | 0% |  | 100% | 53% | 40% | 64% | 257%
|  | Watt Street Inter-change New Housing Development WYNBERG E Regional | 4000000 | 2000000 | 2000000 |  |  |  |  | 4000000 | 100% | 100% |  | 0% | 0% | 0% | 0% | 0%
|  | Balfour Park Transit Precinct Development (Louis Botha Corridor) Renewal Precinct Redevelopment SAVOY ESTATE E City Wide | 21000000 | 16000000 | 5000000 |  |  |  |  | 21000000 | 100% | 100% |  | 100% | 0% | 0% | 0% | 100%
|  | CORR - Louis Botha Corridor of Freedom Traffic Impact Assessment (TIA), Stormwater Masterplan and New COnstriction and Upgrading Renewal Corridors of Freedom Intervention ORANGE GROVE E Regional | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Patterson Park Renewal Park ORANGE GROVE E City Wide | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Upgrade Orchards Substation New Bulk Infrastructure ORCHARDS F Regional | 41948604 | 6570000 | 21512588 |  |  |  |  | 28082588 | 66.95% | 66.95% |  | 50% | 50% | 0% | 33% | 133%
|  | Erf 43-46 Victoria Ext 3(Paterson Park Node) VICTORIA EXT.3 E Regional | 21000000 | 10000000 | 11000000 |  |  |  |  | 21000000 | 100% | 100% |  | 100% | 20% | 0% | 40% | 160%
EMPIRE-PERTH | 8 | Pennyville New Canada Social Housing Project Region B | 65000000 | 65000000 | [5 empty] | 65000000 | 100% | 100% | [5 empty] | 0%
|  | Westbury Development Renewal Precinct Redevelopment WESTBURY B City Wide | 21500000 | 20000000 | 1500000 |  |  |  |  | 21500000 | 7.353% | 7.353% |  | 100% | 100% | 80% | 93% | 373%
|  | CORR - Perth Empire Corridor of Freedom Traffic Impact Assessment (TIA), Stormwater Masterplan and New Constriction and Upgrading Renewal Corridors of Freedom Intervention WESTBURY B Regional | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Penny Flats Social Housing Project Upgrade Region B | 13000000 | 6000000 | 7000000 |  |  |  |  | 13000000 | 100% | 100% |  | 0% | 0% | 0% | 0% | 0%
|  | Brixton MPC (Rec, Sports field and pool) upgrade MAYFAIR WEST B Ward | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Westdene Dam-precinct interventions | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Brixton Social Cluster | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Milpark Precinct Implementation | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
MININING BELT | 9 | Fleurhof Mixed Development (Bulk and internal infrastructure) New Bulk Infrastructure FLEURHOF C Ward | 65804000 | 0 | 0 |  |  |  |  | 0 | 0% | 0% |  | 80% | 20% | 15% | 38% | 153%
|  | Matholesville New Bulk Infrastructure MATHOLESVILLE C Ward | 39000000 | 0 | 0 |  |  |  |  | 0 | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
|  | Bulk supply for the electrification of Fleurhof New Electrification FLEURHOF C | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | RNP040_Crownwood Road Upgrade Renewal Roads: Construction and Upgrades CROWN EXT.2 B Regional | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Mining Belt West Development Corridor (Eastern Precinct):Technical studies on expropriation requirements, to release the necessary land to allow for new roads, road realignments and the widening of road reserves. | 13880000 | 12380000 | 1500000 |  |  |  |  | 13880000 | 100% | 100% |  |  |  |  | 0% | 0%
|  | Construction of a new MPC in Matholesville New Community Centre MATHOLESVILLE C Regional | [7 empty] | 0 | 0% | 0% |  | 0% | 10% | 0% | 3% | 13%
|  | Fleurhof Urban Development Framework Interventions Implementation | 35625000 | 5000000 | 30625000 |  |  |  |  | 35625000 | 100% | 100% |  | 0% | 0% | 0% | 0% | 0%
|  | Detailed Road Master Plan for Mining Belt West Development Corridor | 65000000 | 55000000 | 10000000 |  |  |  |  | 65000000 | 100% | 100% |  | 10% | 0% | 0% | 3% | 13%
|  | Crown City Urban Renewal Strategy | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
TURFFONTEIN | 10 | South Hills Housing Mixed Development New RDP Houses SOUTH HILLS F Ward | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | NR: Nodal Regeneration: Turffontein F Regional | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Turffontein Corridor (Housing) Renewal Corridors of Freedom Intervention TURFFONTEIN F Regional | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | CORR - Turffontein Corridor of Freedom Traffic Impact Assessment (TIA), Stormwater Masterplan and New Construction and Upgrading Renewal Corridors of Freedom Intervention Renewal Stormwater Management Projects JOHANNESBURG F Regional | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Rotunda Park Precinct Turffontein Corridor (JDA) New Precinct Redevelopment TURFFONTEIN F Regional | 3000000 |  | 3000000 |  |  |  |  | 3000000 | 100% | 100% |  | 100% | 50% |  | 50% | 200%
|  | Upgrading of Pioneer Park Renewal Park TURFFONTEIN F Regional | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Turffontein Corridor New Social Housing Project Region E | [7 empty] | 0 | 0% | 0% | [5 empty] | 0%
|  | Wemmer Pan precinct implementation | 11000000 | 11000000 | 0 |  |  |  |  | 11000000 | 100% | 100% | [5 empty] | 0%
|  | MOB - City Deep Freight Hub. Renewal Roads: Construction and Upgrades CITY DEEP F City Wide | 30000000 | 20000000 | 10000000 |  |  |  |  | 30000000 | 100% | 100% | [5 empty] | 0%

## NMB
Project List |  |  | Funding Source (Total Project Value) | [8 empty] | Project Status (% of Project Complete)
Metro | No. of projects reflected on pipeline | Example of Catalytic Projects | Total Value (R'm) | Municipal | Loan | Grant | Province | SOE | PPP | % Total Value | Private Sector Leverage (R'm) | Selection | Preparation | Construction | Completed | Total
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%

## MAN
Project List |  |  | Funding Source (Total Project Value) | [8 empty] | Project Status (% of Project Complete)
Metro | No. of projects reflected on pipeline | Example of Catalytic Projects | Total Value (R'm) | Municipal | Loan | Grant | Province | SOE | PPP | % Total Value | Private Sector Leverage (R'm) | Selection | Preparation | Construction | Completed | Total
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%

## ETK
Project List |  |  | Funding Source (Total Project Value) | [8 empty] | Project Status (% of Project Complete)
Metro | No. of projects reflected on pipeline | Example of Catalytic Projects | Total Value (R'm) | Municipal | Loan | Grant | Province | SOE | PPP | % Total Value | Private Sector Leverage (R'm) | Selection | Preparation | Construction | Completed | Total
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%

## EKU
Project List |  |  | Funding Source (Total Project Value) | [8 empty] | Project Status (% of Project Complete)
Metro | No. of projects reflected on pipeline | Example of Catalytic Projects | Total Value (R'm) | Municipal | Loan | Grant | Province | SOE | PPP | % Total Value | Private Sector Leverage (R'm) | Selection | Preparation | Construction | Completed | Total
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%

## TSH
Project List |  |  | Funding Source (Total Project Value) | [8 empty] | Project Status (% of Project Complete)
Metro | No. of projects reflected on pipeline | Example of Catalytic Projects | Total Value (R'm) | Municipal | Loan | Grant | Province | SOE | PPP | % Total Value | Private Sector Leverage (R'm) | Selection | Preparation | Construction | Completed | Total
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%

## COJ
Project List |  |  | Funding Source (Total Project Value) | [8 empty] | Project Status (% of Project Complete)
Metro | No. of projects reflected on pipeline | Example of Catalytic Projects | Total Value (R'm) | Municipal | Loan | Grant | Province | SOE | PPP | % Total Value | Private Sector Leverage (R'm) | Selection | Preparation | Construction | Completed | Total
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%

## CPT
Project List |  |  | Funding Source (Total Project Value) | [8 empty] | Project Status (% of Project Complete)
Metro | No. of projects reflected on pipeline | Example of Catalytic Projects | Total Value (R'm) | Municipal | Loan | Grant | Province | SOE | PPP | % Total Value | Private Sector Leverage (R'm) | Selection | Preparation | Construction | Completed | Total
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%
[10 empty] | 0% | [5 empty] | 0%

## BCM
Project List |  |  |  |  | Funding Source (Total Project Value) | [9 empty] | Programme Status (% of Project Complete)
[6 empty] | Municipal |  |  |  |  | Private Funding
Metro | No. of projects reflected on pipeline | Integration Zone | Catalytic Programme | Catalytic Projects | Total Value (R'm) | Own | Loan | Grant | Provincial | SOC | PPP | SPV | Private Sector only | Private Sector Leverage % | Inception | Concept | Pre Feasibility | Feasibility | Preparation Finalisation
x
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Note on B3: LisaMay: Not sure if this is needed - it can easily be calculated
Note on O3: LisaMay: calculated field