## Capex
CITY OF JOHANNESBURG
DETAIL MEDIUM TERM CAPITAL BUDGET 2018/19 - 2020/21
PROJECT INFORMATION | [8 empty] | Backlog as at beginning of 2018/19 | Overall Target for 2018/19 as per the SDBIP-USDG |  | QUARTERLY OUTPUTS
Project Number | Project Name | Description | Asset Sub-Class | GPS Location | Ward Location | New or Renewal | Total Estimated Project Cost R 000 | USDG |  |  | 1st Quarter Planned non financial target as per SDBIP - USDG | 1st Quarter Planned financial target as per SDBIP | 1st Quarter ACHIEVED non financial | 1st Quarter ACHIEVED financial | 2nd Quarter Planned non financial target as per SDBIP - USDG | 2nd Quarter Planned financial target as per SDBIP -USDG | 2nd Quarter ACHIEVED non financial-USDG | 2nd Quarter ACHIEVED financial-USDG | 3rd Quarter Planned non financial target as per SDBIP - USDG | 3rd Quarter Planned financial target as per SDBIP -USDG | 3rd Quarter ACHIEVED non financial - USDG | 3rd Quarter achieved financial target as per SDBIP -USDG | 4th Quarter Planned non financial target as per SDBIP - USDG | 4th Quarter Planned financial target as per SDBIP -USDG | 4th Quarter ACHIEVED non financial - USDG | 4th Quarter achieved financial target as per SDBIP -USDG | Summary of Planned output as per SDBIP | Summary of Actual output for 2017/18 | Actual output for 2017/18 as per Annual Report | Variation | Reason(s) for variation | Remedial action
HEALTH & COMMUNITY DEVELOPMENT: SOCIO ECONOMIC AMENITIES PROJECTS
22675 | Rec- Construction of Drieziek MPC (ACH and Sports and Recreation) | 0 | Community Assets | 28.0393061041832;-26.2068880974665 | 124 | Existing | 25000 | 15000 |  |  | 5% | 1126.6148 |  |  | 20% | 6373.3852 |  |  | 50% | 6373.3852 |  |  | 100% | 1126.6148
| Sub Total | [6 empty] | 15000
6566 | Bophelong Clinic | Planning, design, layout of clinic, construction of building and carports, landscaping and paving, furniture, medical equipment and signage.. | Community Assets | 27.8183061629534;-26.2198848356089 | 50 | New | 49000 | 10000 |  |  | Tender Stage | 826.1842 |  |  | Tender Stage | 4673.8158 |  |  | Start of Construction | 4673.8158 |  |  | Start of Construction | 826.1842
3826 | Claremont Renewal Clinic CLAREMONT B Ward | Planning, design, layout of clinic, construction of building and carports, landscaping and paving, furniture, medical equipment and signage.. | Community Assets | 27.9578093374861;-26.1807051129075 | 82 | Existing | 10000 | 10000 |  |  | Completion of Construction | 10000 |  |  | Commissioning of Facility |  |  |  |  | 0
3975 | Florida clinic New Clinic FLORIDA EXT C Ward | Planning, design, layout of clinic, construction of building and carports, landscaping and paving, furniture, medical equipment and signage.. | Community Assets | 27.9124195128679;-26.1714037793068 | 70 | New | 17000 | 17000 |  |  | Completion of Construction | 17000 |  |  | Commissioning of Facility |  |  |  |  | 0
| Sub Total | [6 empty] | 37000
HOUSING & JOSHCO : INTERNAL SERVICES PROJECTS
3452 | PRINCESS PLOT New Bulk Infrastructure PRINCESS C Regional |  | Water Supply Infrastructure | 27.8490606807537;-26.1315201059384 | 71 | New | 83000 | 15000 |  | Procurement & detailed designs & construction for phase 1 | Procurement of a Civil Engineer | 1126.6148 |  |  | Preliminary Design Report | 6373.3852 |  |  | Detailed Design | 6373.3852 |  |  | Construction of Internal Roads | 1126.6148
3456 | COSMO CITY PHASE 2 ( MALIBONGWE RIDGE) New Bulk Infrastructure COSMO CITY C Regional |  | Water Supply Infrastructure | 27.9358282392522;-26.0170922227796 | 100 | New | 464493.743 | 173994 |  |  | None | 13932.0193 |  |  | Procurement | 78814.9807 |  |  | 1. Link water & sewer. 2. Internal water & sewer. | 78814.9807 |  |  | 1. Retention ponds. 2. Internal roads & stormwater. 3. Link stormwater. 4. Link roads. | 13932.0193
3457 | Diepsloot Redevelopment Northern Farms New Bulk Infrastructure DIEPSLOOT A.H. A Regional | Bulk Infrastructure | Water Supply Infrastructure | 28.0123589350842;-25.9351658815782 | 113 | New | 100000 | 62000 |  | Bridge and Porcupine road | Construction of bridge | 4656.6746 |  |  | Construction of bridge | 26343.3254 |  |  | Construction of bridge | 26343.3254 |  |  | Bridge | 4656.6746
6571 | Bramfischerville Ext 7 & 8 New Bulk Infrastructure | Bulk Infrastructure | Roads Infrastructure | 27.8396987915039;-26.1984193437349 | 49 | New | 55000 | 25000 |  |  |  | 1877.6914 |  |  |  | 10622.3086 |  |  |  | 10622.3086 |  |  |  | 1877.6914
22115 | Kanana Park Ext 2 | Bulk Infrastructure | Water Supply Infrastructure | 27.8976774215698;-26.4127997076162 | 6 | New | 91000 | 11000 |  |  |  | 2403.445 |  |  |  | 13596.555 |  |  |  | 13596.555 |  |  |  | 2403.445
22183 | Madala Hostel Redevelopment | Hostel redevelopment | Water Supply Infrastructure | 28.0985641479492;-26.1155235176985 | 81 | Existing | 25000 | 15000
22125 | Informal Settlements Detailed Designs | Informal settlements provision of basic services | Water Supply Infrastructure | 27.8579807281494;-26.4799269979794 | 3 | New | 14000 | 14000 |  |  |  | 1051.5072 |  |  |  | 5948.4928 |  |  |  | 5948.4928 |  |  |  | 1051.5072
4255 | Land Acquisition for Housing New Bulk Infrastructure JOHANNESBURG F City Wide |  |  | 27.7297805249691;-26.2237563845643 | City Wide | Land | 219288 | 20000 |  | Land Acquisition for Housing |  | 1502.1531 |  |  |  | 8497.8469 |  |  |  | 8497.8469 |  |  |  | 1502.1531
2565 | Braamfischerville Ext 12&13:Roads and Stormwater Management Systems including a Pedestrian Bridge New Bulk Infrastructure BRAM FISCHERVILLE EXT.13 C Ward | Infrastructure Project: | Roads Infrastructure | 27.8215961332899;-26.194528017565 | 49 | New | 49498 | 18498 |  | Construction of internal roads & stormwater |  | 1389.3414 |  |  |  | 7859.6586 |  |  |  | 7859.6586 |  |  |  | 1389.3414
2274 | Tshepisong Proper - Bulk Stormwater New Bulk Infrastructure TSHEPISONG C Ward | New Bulk infrastructure | Storm water Infrastructure | 27.8080266101613;-26.1922065941378 | 128 | New | 64074.2 | 25000 |  |  |  | 1877.6914 |  |  |  | 10622.3086 |  |  |  | 10622.3086 |  |  |  | 1877.6914
2891 | Matholesville New Bulk Infrastructure MATHOLESVILLE C Ward | New Bulk infrastructure | Water Supply Infrastructure | 27.8441670240656;-26.1703345125994 | 127 | New | 40000 | 10000 |  |  |  | 751.0765 |  |  |  | 4248.9235 |  |  |  | 4248.9235 |  |  |  | 751.0765
3184 | Elias Motsoaledi New Bulk Infrastructure DIEPKLOOF EXT.10 D Ward |  | Solid Waste Infrastructure | 27.9255294799805;-26.2642278871211 | 24 | New | 29126.857 | 5000 |  |  |  | 375.5383 |  |  |  | 2124.4617 |  |  |  | 2124.4617 |  |  |  | 375.5383
3185 | Klipspruit/Kliptown New Bulk Infrastructure (Housing project around the Walter Sisulu Square) KLIPSPRUIT D Ward |  | Roads Infrastructure | 27.8890943527222;-26.2779036485685 | 17 | New | 122000 | 37000 |  | Construction of Bulk and internal services | Site establishment and 5% construction | 3755.3827 |  |  | construction of road and storm water progress 30 % | 21244.6173 |  |  | construction of road and storm water 70% | 21244.6173 |  |  | Project Completion | 3755.3827
3186 | Lehae Ext 1: Development of Bulk Link and Internal Infrastructure | New Bulk infrastructure | Roads Infrastructure | 27.8806175277428;-26.3480306431532 | 122 | New | 111000 | 21000
3224 | Klipvieroog (1914) New Bulk Infrastructure LEHAE G Ward |  | Water Supply Infrastructure | 27.892474988093;-26.3456852930334 | 122 | New | 25000 | 13000 |  |  |  | 1126.6148 |  |  |  | 6373.3852 |  |  |  | 6373.3852 |  |  |  | 1126.6148
3225 | Poortjie Dark City (3000) New Bulk Infrastructure POORTJIE G Ward | New Bulk infrastructure | Water Supply Infrastructure | 27.7679428648968;-26.457605818767 | 5 | New | 95000 | 15000 |  | Procurement for a Civil Engineer and Contractor for the construction of internal roads and stormwater | Procurement of a Civil Engineer | 1126.6148 |  |  |  | 6373.3852 |  |  |  | 6373.3852 |  |  |  | 1126.6148
3140 | Kya Sands / Lion Park New Bulk Infrastructure KYA SAND EXT.20 A Ward |  | Water Supply Infrastructure | 27.9473445741791;-26.0219831378493 | 96 | New | 15000 | 5000 |  |  |  | 3004.3062 |  |  |  | 16995.6938 |  |  |  | 16995.6938 |  |  |  | 3004.3062
3197 | Kanana Park Ext 1 (788) New Bulk Infrastructure KANANA PARK EXT.1 G Ward |  | Water Supply Infrastructure | 27.9004183784679;-26.4192321467007 | 6 | New | 85000 | 25000 |  | Procurement for a Civil Engineer and Contractor for the construction of internal roads and stormwater | Procurement of a Civil Engineer | 2816.5371 |  |  | EIA scoping report | 15933.4629 |  |  | None | 15933.4629 |  |  | Record of Decision (RoD) | 2816.5371
3198 | Vlakfontein Proper (1519) New Bulk Infrastructure VLAKFONTEIN G Ward | New Bulk infrastructure | Water Supply Infrastructure | 27.8784805835832;-26.3751161112762 | 122 | New | 30000 | 20000 |  |  |  | 1502.1531 |  |  |  | 8497.8469 |  |  |  | 8497.8469 |  |  |  | 1502.1531
3199 | Vlakfontein Ext 1 (935) New Bulk Infrastructure VLAKFONTEIN EXT.1 G Ward | New Bulk infrastructure | Roads Infrastructure | 27.8885989636287;-26.3729304114271 | 122 | New | 20000 | 8005.981 |  |  |  | 751.0765 |  |  |  | 4248.9235 |  |  |  | 4248.9235 |  |  |  | 751.0765
3202 | Vlakfontein Ext 3 (2045) New Bulk Infrastructure VLAKFONTEIN EXT.3 G Ward | New Bulk infrastructure | Water Supply Infrastructure | 27.8885594603767;-26.386854042231 | 122 | New | 75000 | 25000 |  | Commence Construction of roads | Procurement of a Civil Engineer | 3004.3062 |  |  | Detailed designs & procurement of a contractor | 16995.6938 |  |  | Procurement of a contractor | 16995.6938 |  |  | Construction of internal roads | 3004.3062
3203 | Finetown Proper (1878 stands) New Bulk Infrastructure FINETOWN G Ward |  | Water Supply Infrastructure | 27.8652407729517;-26.4158569370031 | 7 | New | 60000 | 30000 |  |  |  | 2253.2296 | 569143.2742 |  |  | 12746.7704 | 450000 |  |  | 12746.7704 | 2253229.647 |  |  | 2253.2296 | 12746770.353
3204 | Kanana Park Ext 3,4 & 5 New Bulk Infrastructure KANANA PARK EXT.3 G Ward |  | Roads Infrastructure | 27.8996216036845;-26.4241207778214 | 6 | New | 110000 | 15000 |  |  |  | 1126.6148 |  |  |  | 6373.3852 |  |  |  | 6373.3852 |  |  |  | 1126.6148
3207 | Drieziek Ext.3 (2989) New Bulk Infrastructure DRIEZIEK EXT.3 G Ward |  | Water Supply Infrastructure | 27.8403769243252;-26.465733824479 | 5 | New | 110000 | 30000 |  |  |  | 3304.7368 | 834743.4688 |  |  | 18695.2632 | 660000 |  |  | 18695.2632 | 3304736.8157 |  |  | 3304.7368 | 18695263.1843
3208 | Drieziek Ext.5 (1540) New Bulk Infrastructure DRIEZIEK EXT.5 G Ward |  | Water Supply Infrastructure | 27.8312383659454;-26.4735860595731 | 5 | New | 84000 | 34000 |  |  |  | 2553.6603 | 645029.044 |  |  | 14446.3397 | 510000 |  |  | 14446.3397 | 2553660.2666 |  |  | 2553.6603 | 14446339.7334
3211 | Ennerdale South (1902 stands) (Formerly Finetown Proper) New Bulk Infrastructure ENNERDALE G Ward |  | Water Supply Infrastructure | 27.8539509556037;-26.4078847863411 | 7 | New | 60000 | 30000 |  | Commence with construction of Internal roads | Procurement of a Civil Engineer | 2253.2296 |  |  | Detailed designs & procurement of a contractor | 12746.7704 |  |  | Procurement of a contractor | 12746.7704 |  |  | Construction of internal roads | 2253.2296
2683 | Fleurhof Mixed Development (Bulk and internal infrastructure) New Bulk Infrastructure FLEURHOF C Ward |  | Water Supply Infrastructure | 27.9157415195;-26.1996401459194 | 70 | New | 65804 | 65804 |  |  |  | 4942.3841 |  |  |  | 27959.6159 |  |  |  | 27959.6159 |  |  |  | 4942.3841
2752 | Meadowlands Hostel Renewal Building Alterations MEADOWLANDS D Ward | Hostel Renewal | Other Assets | 27.8980732015863;-26.2144514402862 | 43 | Existing | 30000 | 10000
2755 | Site and Services - Formalisation of informal settlements across the City. Renewal Bulk Infrastructure JOHANNESBURG F City Wide | 0 | Roads Infrastructure | 28.0424703564495;-26.1943040206008 | City Wide | Existing | 250000 | 120000 |  |  |  | 9012.9186 |  |  |  | 50987.0814 |  |  |  | 50987.0814 |  |  |  | 9012.9186
2733 | Lakeside Ext 3,4 & 5: Roads and Bulk Stormwater Systems New Bulk Infrastructure |  | Water Supply Infrastructure | 27.8816036686546;-26.5127743465399 | 2 | New | 125000 | 30000 |  | Commence with construction of Internal roads | Procurement of a Civil Engineer | 3004.3062 |  |  | Detailed designs & procurement of a contractor | 16995.6938 |  |  | Procurement of a contractor | 16995.6938 |  |  | Construction of internal roads | 3004.3062
2771 | Helen Josephs Refurbishment and Upgrading of Women's Hostel Renewal Building Alterations ALEXANDRA EXT.52 E Ward | Refurbishment and Upgrading of Women's Hostel. | Other Assets | 28.0877148517014;-26.1050811368797 | 91 | Existing | 20000 | 20000 |  | Construction of internal services on Erf 52 | Advertising of Helen Joseph construction tender | 1502.1531 |  |  | Site establishment and 5% construction | 8497.8469 |  |  | construction of road and storm water 20% | 8497.8469 |  |  | construction of road and storm water 50% | 1502.1531
2566 | Lufhereng Mixed Development (Bulk, Link & Internal Infrastructure Roads, Storm Water Management Systems, Sewer & Water for 24 000 houses) | 0 | Other Assets | 0 | 0 | Existing | 272000 | 100000
0 | Diepkloof Hostel | 0 | Other Assets | 0 | 0 | Existing | 70000 | 15000
3159 | Moffat View Ext 6 New Bulk Infrastructure MOFFAT VIEW EXT.6 F Ward | 0 | Other Assets | 0 | 0 | Existing | 8000 | 8000
| Sub Total | [6 empty] | 1071301.981
22292 | 106 Claim Street Inner City Building Conversion Region F |  | Investment Properties | 28.0483719706535;-26.1891857991707 | 63 | Existing | 30000 | 25000 |  |  |  | 2253.2296 |  |  |  | 12746.7704 |  |  |  | 12746.7704 |  |  |  | 2253.2296
| Sub Total | [6 empty] | 25000
CITY POWER: ELECTRICITY PROJECTS
4280 | Electrification of various Informal Settlements (Plot 8 Lindhaven, Kliptown Ext11, Princess Plot 61, Freedom Charter Square, Ruimsig Portion 77, Westgate development Princess Plot) New electrification JOHANNESBURG F City wide | 0 | Electrical Infrastructure | 27.88330078125;-26.2876435793318 | City Wide | New | 355071.215 | 85824.223 |  |  | Internal Approval | 4223.2174 |  |  | Procurement | 3339.1378 |  |  | Construction | 16719.6541 |  |  | Commissioning | 61541.9904
| Sub Total | [6 empty] | 85824.223
JOHANNESBURG WATER: WATER PROJECTS
2571 | Deep South/ Orange Farm: Doornkop West/Protea Glen district:Upgrade water infrastructure | 0 | Water Supply Infrastructure | 27.8120693212063;-26.2831794768823 | 135 | Existing | 18000 | 18000 |  | 100% construction completion | Project realised 30% complete | 5000000 |  |  | Project realised 55% complete | 7000000 |  |  | Project realised 100% complete | 6000000
2246 | Roodepoort/Diepsloot: Planned Replacement Watermains | Planned Replacement Watermains. | Water Supply Infrastructure | 27.9692363692448;-26.052101231738 | 101 | New | 100000 | 40000
2198 | Basic Water Service New Basic Water and Sewer Services | Basic Water Service New Basic Water and Sewer Services | Water Supply Infrastructure | 27.8599088337147;-26.4621159811304 | 4 | Existing | 65000 | 30000 |  | 5714 | Procurement | 0 |  |  | 1055 house holds | 10047.538 |  |  | 4550 house holds | 12211.116 |  |  | 109 house holds | 7741.346
2375 | Orange farm/ Deep South: Lenasia Water Upgrade | Lenasia Water Upgrade. | Water Supply Infrastructure | 27.8518788345554;-26.3314033265679 | 9 | New | 28000 | 28000 |  | 100% overall construction completion of both pumpstation & Risisng Main& Award of tender for Lenasia Resevoir | Appointment of service providers & 15% construction completion | 9000 |  |  | 40% construction completion of the pump station & Pipeline | 6000 |  |  | 75% construction completion of the pump station & Pipeline | 8000 |  |  | 100% construction completion of the pump station & Pipeline | 5000
6513 | Soweto: Meadowlands Reservoir 19.8ML | Meadowlands Reservoir 19.8ML. | Water Supply Infrastructure | 27.8934288024902;-26.21486053276 | 43 | New | 7000 | 7000
21828 | Diepsloot Water Upgrade | Region A - MIDRAND-Diepsloot Water Upgrade | Water Supply Infrastructure | 28.0097008449957;-25.9336596960588 | 113 | Existing | 53234.777 | 27733.796
| Sub Total | [6 empty] | 150733.796
JOHANNESBURG WATER: SANITATION PROJECTS
3586 | Roodepoort/ Diepsloot: Planned Replacement Sewer mains | Roodepoort/ Diepsloot: Planned Replacement Sewer mains. | Sanitation Infrastructure | 27.8634451513253;-26.160655821412 | 84 | Existing | 60600.386 | 13614
3628 | Soweto: Dube Sewer Upgrade | Soweto: Dube Sewer Upgrade. | Sanitation Infrastructure | 27.8949002470729;-26.2397146375485 | 38 | Existing | 3756 | 3756
3638 | Soweto: Bramfisherville Sewer Upgrade | Soweto: Bramfisherville Sewer Upgrade. | Sanitation Infrastructure | 27.8534317016602;-26.1971871236314 | 49 | Existing | 4000 | 4000
6527 | Midrand: Ivory Park North Upgrade Sewer | Midrand: Ivory Park North Upgrade Sewer. | Sanitation Infrastructure | 28.2040023710579;-25.9815464489142 | 77 | Existing | 1600 | 1600 |  | 100% construction completion | 100% Complete | 1600
22511 | Soweto: Anthea Nancefield Sewer (Klipspruit River) Phase 1 | 0 | Sanitation Infrastructure | 27.9175742994994;-26.2311009332049 | 39 | New | 50000 | 30000
| Sub Total | [6 empty] | 52970
JOHANNESBURG ROADS AGENCY: ROADS & STORMWATER PROJECTS
2706 | CONV - Conversion of Open Drains to Underground/Covered Drains in Ivory Park and surrounding areas. Renewal Stormwater Management Projects IVORY PARK EXT.7 A Ward |  | Roads Infrastructure | 28.1974601699039;-25.9935479148016 | 111 | Existing | 25000 | 5000 | TBC | 0.5km | 0km | 500 |  |  | 0.1km | 1000 |  |  | 0.2km | 1500 |  |  | 0.2km | 2000
2941 | MISCL - Pedestrian Bridge in Diepsloot (No. 4) New Bridges (Pedestrian and Vehicles) DIEPSLOOT WES EXT.2 A Ward |  | Roads Infrastructure | 28.0109310150146;-25.9426479237265 | 113 | New | 6000 | 6000 | 1 bridge | 100% bridge completion | 0% bridge- (site establishment) | 600 |  |  | 20% bridge- inprogress | 2000 |  |  | 50% bridge- inprogress | 1000 |  |  | 100% bridge complete | 2400
2953 | MISCL - Pedestrian Bridge in Klipspruit West. New Bridges (Pedestrian and Vehicles) KLIPSPRUIT WEST D Ward |  | Roads Infrastructure | 27.8788502619061;-26.2822867881603 | 19 | New | 5000 | 5000 | 1 bridge | 100% bridge completion | 0% bridge- (site establishment) | 500 |  |  | 20% bridge- inprogress | 2000 |  |  | 50% bridge- inprogress | 1000 |  |  | 100% bridge complete | 1500
2973 | MISCL - Tarring of Gravel Roads: Lawley. New Roads: Construction and Upgrades LAWLEY EXT.1 G Ward | 0 | Roads Infrastructure | 27.8112030300129;-26.392976574551 | 121 | New | 30000 | 25000 | 16.41km | 2.7km | 0km | 3000 |  |  | 0km | 5000 |  |  | 0.7km | 10000 |  |  | 2km | 12000
2389 | MISCL - Emergency, Critical and Urgent Depot Stormwater Improvements. New Stormwater Management Projects JOHANNESBURG F City Wide |  | Roads Infrastructure | 27.6403465480266;-26.2352165422455 | City Wide | New | 135000 | 45000 | TBC | 100% implementation | 10%- in progress | 5000 |  |  | 20%- in progress | 10000 |  |  | 30%- in progress | 20000 |  |  | 40% 100% completion) | 15000
2393 | MISCL - Tarring of Gravel Roads: Orange Farm and Surrounding Areas. New Roads: Construction and Upgrades ORANGE FARM G Ward | 0 | Roads Infrastructure | 27.8763736411027;-26.4869289926152 | 3 | New | 120000 | 35000 | 64.4km | 4.km | 0km | 5000 |  |  | 0km | 10000 |  |  | 2km | 15000 |  |  | 2km | 20000
2399 | MISCL - Tarring of Gravel Roads: Ivory Park and Surrounding Areas. New Gravel Road IVORY PARK EXT.9 A Ward | 0 | Roads Infrastructure | 28.2056580964987;-25.9904388135577 | 133 | New | 100000 | 25000 | 52.8km | 2.7km | 0km | 3000 |  |  | 0km | 5000 |  |  | 0.7km | 10000 |  |  | 2km | 12000
2410 | MISCL - Tarring of Gravel Roads: Diepsloot. New Roads: Construction and Upgrades DIEPSLOOT WEST EXT.3 A Ward | 0 | Roads Infrastructure | 28.0114383586048;-25.9243018597697 | City Wide | New | 126000 | 25000 | 17.1km | 2.4km | 0km | 2000 |  |  | 0km | 5000 |  |  | 1km | 8000 |  |  | 1km | 11000
2417 | MISCL - Tarring of Gravel Roads: Doornkop/Thulani. New Roads: Construction and Upgrades DOORNKOP D Ward | 0 | Roads Infrastructure | 27.8097476355532;-26.2354339251624 | 53 | New | 130800 | 25000 | 35km | 2.4km | 0km | 2000 |  |  | 0km | 5000 |  |  | 1km | 8000 |  |  | 1km | 11000
2496 | MISCL - Tarring of Gravel Roads: Bram Fischerville. New Roads: Construction and Upgrades BRAM FISCHERVILLE D Ward | Roads and Stormwater Infrastructure Project: | Roads Infrastructure | 27.861971621682;-26.2078978943346 | 44 | New | 124000 | 24000 | TBC | 0.5km | 0km | 1000 |  |  | 0.1km | 2000 |  |  | 0.1km | 3000 |  |  | 0.3km | 4000
3986 | MISCL - Tarring of Gravel Roads: Drieziek. New Roads: Construction and Upgrades DRIEZIEK G Ward | 0 | Roads Infrastructure | 27.843071884975;-26.4699738075319 | 5 | New | 96273 | 26273 | 56km | 2.6km | 0km | 2000 |  |  | 0km | 3000 |  |  | 0.6km | 5000 |  |  | 2km | 10000
3819 | MISCL - Tarring of Gravel Roads: Tshepisong. New Roads: Construction and Upgrades TSHEPISONG C Ward | 0 | Roads Infrastructure | 27.8056241504648;-26.1888039297038 | 128 | Existing | 100000 | 15150 | 37.4km | 2.7km | 0km | 3000 |  |  | 0km | 5000 |  |  | 0.7km | 10000 |  |  | 2km | 12000
3788 | CONV - Conversion of Open Drains to Underground/Covered Drains in Orange Farm and Surrounding Areas. Renewal Stormwater Management Projects ORANGE FARM G Ward |  | Storm water Infrastructure | 27.8703307919204;-26.5031837819974 | 2 | New | 80000 | 20000 | TBC | 1km | 0km | 2000 |  |  | 0.2km | 5000 |  |  | 0.3km | 5000 |  |  | 0.5km | 8000
3789 | CONV - Conversion of Open Drains to Underground/Covered Drains in Bram Fischerville. Renewal Stormwater Management Projects BRAM FISCHERVILLE C Ward |  | Storm water Infrastructure | 27.8459167387336;-26.2004409218976 | 49 | Existing | 30000 | 10000 | TBC | 0.5km | 0km | 1000 |  |  | 0.1km | 2000 |  |  | 0.1km | 3000 |  |  | 0.3km | 4000
4205 | CATCH - Implementation of CBP Stormwater Masterplanning: Soweto. New Stormwater Management Projects ORLANDO WEST D Regional |  | Storm water Infrastructure | 27.9110791971117;-26.2353899165092 | 39 | Existing | 85000 | 18009 | TBC | 100% implementation | 5%- inprogress | 2000 |  |  | 10%- in progress | 3000 |  |  | 25%- inprogress | 10000 |  |  | 60%- 100% complete | 10000
4206 | MISCL - Tarring of Gravel Roads: Kaalfontein. New Roads: Construction and Upgrades KAALFONTEIN EXT.2 A Ward | 0 | Roads Infrastructure | 28.1867159975332;-25.9890740253046 | 92 | New | 69000 | 25000 | 10.7km | 2.7km | 0km | 3000 |  |  | 0km | 5000 |  |  | 0.7km | 10000 |  |  | 2km | 12000
4209 | MISCL - Tarring of Gravel Roads: Mayibuye. New Roads: Construction and Upgrades COMMERCIA A Ward | 0 | Roads Infrastructure | 28.1494785006374;-26.0361852632358 | 110 | New | 100000 | 25000 | 5.6km | 2.7km | 0km | 3000 |  |  | 0km | 5000 |  |  | 0.7km | 10000 |  |  | 2km | 12000
4135 | MISCL - Tarring of Gravel Roads: Poortjie. New Roads: Construction and Upgrades POORTJIE G Ward | 0 | Roads Infrastructure | 27.7669183243719;-26.4557727230935 | 5 | New | 30000 | 30000 | 6.5km | 2.7km | 0km | 2000 |  |  | 0km | 5000 |  |  | 0.7km | 20000 |  |  | 2km | 30000
4136 | MISCL - Tarring of Gravel Roads: Slovoville New Roads: Construction and Upgrades SLOVOVILLE D Ward | 0 | Roads Infrastructure | 27.7811787003332;-26.2161476472896 | 53 | New | 100000 | 25000 | 9km | 2.7km | 0km | 3000 |  |  | 0km | 5000 |  |  | 0.7km | 10000 |  |  | 2km | 12000
| Sub Total | [6 empty] | 414432
| Grand Total | [6 empty] | 1852262
| Check Annexure A | Check Annexure A
| Check Jsip | Check Cims | [5 empty] | -1852262