## USDG PLAN
NELSON MANDELA BAY MUNICIPALITY
URBAN SETTLEMENTS DEVELOPMENT GRANT PLAN 2018/19
Project Name | Overall Financial Target for 2018/19 as per | Overall Financial Target for 2018/19 as per | Overall Non financial Target for 2018/19 as per the | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 3rd Quarter | 3rd Quarter | 4th Quarter | 4th Quarter
| SDBIP-USDG REVISED | SDBIP-USDG | SDBIP-USDG | Planned Financial -USDG | Planned Non financial - USDG | Planned Financial -USDG | Planned non Financial-USDG | Planned Financial -USDG | Planned non Financial-USDG | Planned Financial output | Planned Non Financial | 3% allocation | BUDGET EXCL 3% | BUDGET EXCL VAT
WATER AND SANITATION
Provision of bulk water and sanitation services for the upgrading of informal settlements | 433487360 | 598911000 | 2500 | 43348736 | 500 | 173394944 | 1000 | 303441152 | 1750 | 433487360 | 2500 | 13004620.8 | 420482739.2 | 365637164.5217
ROADS AND STORMWATER
Tarring of gravel roads | 70000000 | 91200000 | 9km | 7000000 | 0 km | 28000000 | 0 km | 49000000 | 4km | 70000000 | 9km
| 0 |  |  |  | (appoint-ment of contractors and site preparation) |  | (box cut and layer works) |  |  | 0
Stormwater | 10000000 |  | 100% completion of project | 2500000 | 25% of project completed | 5500000 | 55% of project completed | 10000000 | 100% of project completed | N/A | N/A | 2100000 | 67900000 | 59043478.2609
HUMAN SETTLEMENTS
Servicing of sites | 183456930 | 230520000 | 2500 | 18345693 | 500 | 73382772 | 1000 | 128419851 | 1750 | 183456930 | 2500
(water, sanitation, basic roads) | 0 | [8 empty] | 0
Purchasing of land | 45000000 |  | 2 parcels of land procured | 0 | 0 | 0 | 0 | 0 | 0 | 45000000 | 2 parcels of land procured | 5503707.9 | 177953222.1 | 154741932.2609
HEALTH AND SOCIAL DEVELOPMENT
Development of Public Open Spaces | 8565217 | 20700000 | 5 Public Open Spaces | 856521.7 | 0 | 3426086.8 | 1 Public Open Space | 5995651.9 | 3 Public Open Spaces | 8565217 | 5 Public Open Spaces | 256956.51 | 8308260.49 | 7224574.3391
| 0 |  |  |  | (Prioritisation of sites and procurement)
Development of Cemeteries | 4217391 | 5000000 | 1 Cemetery | 421739.1 | 0 | 1686956.4 | 20% completion | 2952173.7 | 50% completion | 4217391 | 1 Cemetery | 126521.73 | 4090869.27 | 3557277.6261
| 0 |  |  |  | (Prioritisation of sites and procurement)
ENERGY
Public lighting | 7494041 | 9400000 | 960 installations | 749404.1 | 240 | 2997616.4 | 480 | 5245828.7 | 720 | 7494041 | 960 | 224821.23 | 7269219.77 | 6321060.6696
(Area and residential lighting) | 0 |  |  |  | installations |  | installations |  | installations |  | installations
Refurbishing of distribution sub-stations | 1686957 | 2000000 | 4 substations | 168695.7 | 1 substation | 674782.8 | 2 substations | 1180869.9 | 3 substations | 1686957 | 4 substations | 50608.71 | 1636348.29 | 1422911.5565
0
Note: Values above exclude VAT and 3% operational expenses. | [11 empty] | 21267236.88 |  | 597948399.2348

## MTSF
NELSON MANDELA BAY MUNICIPALITY - SUMMARY OF 5-YEAR MTSF TARGETS
MTSF TARGET 2019 | National 5 Yr MTSF Target for Metro | Annual MTSF Target | 2014/15 Achieved | 2015/16 Achieved | 2016/17 Achieved | 2017/18 Target | 2018/19 Target
750 000 households in informal settlements upgraded to Phase 2 of the Informal Settlements Upgrading Programme | 14 810 | 2 962
Individual households (serviced sites – not metered) |  |  | 4 035 | 3 003 | 4 004 | 3000 | 2500
Water and Sanitation
Total to date towards MTSF Target |  |  |  | Sub-total | 11 042
[5 empty] | 1 043 | (2017/18 Mid-year actual)
12 085
Individual Households
Water |  |  | 1 041 | 1 749 | 1 130 | 582 | 1500
Sanitation |  |  | 1 041 | 1 749 | 1 130 | 582 | 1500
Electricity |  |  | 2 215 | 1 945 | 3 432 | 2 000 | 1500
Title Deeds:
563 000 for new developments |  |  | 894 | 528 | 856 | 1 000 | 1 000
Pre-1994 housing stock |  |  | 163 | 323 | 508 | 200 | 200
Post-1994 housing stock
10 000 of hectares of well-located land