## Financial Plan
UTHUKELA DISTRICT MUNICIPALITY RECOVERY PLAN
LINE | KEY FOCUS AREAS | OUTPUTS | ACTIVITIES | RESPONSIBLE | START DATE | FINISH DATE | MEANS OF VERIFICATION | PROGRESS
NO |  |  |  | PERSON |  |  |  | (25 SEPT 19)
KPA 1: INSTITUTIONAL INTERVENTIONS
1.1 | Organizational Structure | Reviewed organizational structure and job descriptions | Review and streamline positions according to organizational needs. Allocate more human resources to core-business units | Ministerial Rep | 2019-05-01 | 2019-12-31 | Council resolutions on reviewed organizational structure | Draft Organisational structure has been compiled. Service provider’s contract with Cogta expired. UTDM is following SCM processes to secure her services for another two months
MM
GM: Corp S
Mgr: HR
1.2 |  |  | Review job descriptions, draft them according to task grade format, consult with labour and obtain Council’s approval. | Ministerial Rep | 2019-05-01 | 2019-12-31 | Council resolutions on reviewed job descriptions | Not achieved yet.. The activity is dependent to 1.1 above
MM
GM: Corp S
Mgr: HR
1.3 | Salary parities, Labour disputes and High Labour related costs | Standardised salary scales according to Task Grade system | Placement and re-deployment of staff core-business units | MM | 2019-10-01 | 2019-12-31 | Filled positions | Not achieved. The activity is dependent to 1.1 above
All GMs
Mgr: HR
1.4 |  |  | Submission of the new organisational structure and job description for Job Evaluation | MM | 2019-10-01 | 2019-12-31 | Implementation of the Outcome of Job Evaluation process | Not achieved. The activity is dependent to 1.1 above
All GMs
Mgr: HR
1.5. |  | Reviewed remuneration and benefits related HR policies | Review remuneration and benefits related HR policies to define criterion for benefits like municipal mobile phone, car and stand-by allowance etc | MM | 2019-10-01 | 2019-12-31 | Council Resolution adopting reviewed HR Policies | Service Provider has been instructed to review policy with a view of limiting discretionary provisions but align benefits to job requirement(s)/ need for such benefit or tool of trade
All GMs
Mgr: HR
1.6 |  | Functional Local Labour Forum ( LLF) | Review LLF’s TORs, reconstitute and train the members of the forum and adopt a new schedule of meetings | MM | 2019-10-01 | 2019-12-31 | Council Resolution on adopted HR Strategy | Meeting held on 16 September 2019 with shop stewards and management. SALGA has been requested to run a workshop for the members of the LLF
All GMs
Mgr: HR
1.7 | Staff Discipline | Employee Code of Conduct communicated to all staff | Communicate the Code of Conduct for municipal staff and the reasons why the need for disciplined workforce | MM | 2019-09-01 | 2019-12-31 | Staff communique and circulars | HR has been requested to facilitate the signing of the Code of Conduct by all staff.
All GMs
All Mgrs
Snr HR
1.8 |  | All disciplinary cases finalised | Appoint initiators and chairpersons of disciplinary cases | Ministerial Rep | 2019-09-01 | 2019-12-31 | Schedule of completed cases | Existing disciplinary cases are being finalised, with new cases being instituted as and when they arise
|  |  | Schedule disciplinary hearings | MM
All GMs
Snr M: HR
KPA 2: GOVERNANCE AND PUBLIC PARTICIPATION INTERVENTIONS
GOVERNANCE
2.1 | Strengthening of Oversight structures | All members of MPAC training on financial and organisational performance matters with a special focus of consequence management | Organise MPAC training sessions with COGTA and Salga | Ministerial Rep | 2019-09-01 | 2019-12-31 | Training Attendance Register | Cogta has been requested to conduct training for the MPAC members. Awaiting dates.
MM
GM: Corp S
MM
2.2 |  | Regular meetings of Audit Committee | Review schedule of meetings for the Audit Committee and ensure that meetings sit as per scheduled | Ministerial Rep | 2019-09-01 | 2019-12-31 | Meeting’s agenda, and attendance Registers | The last Audit Committee meeting was held on the 24th of August 2019. Next meeting is scheduled for 25th of October 2019
MM
CAE
2.3 | Improved Audit Outcomes | Resolved 2017/18 Audit queries | Ensure that Audit Action Plan is fully implemented | Ministerial Rep | 2019-09-01 | 31 November 2019 | Better 2018/19 Audit Outcome | Last year’s qualifications have been resolved. Audit is underway
MM
All GMs
Mgr: IA
2.4 |  | Better Auditor General’s Audit Opinion 2018/19 | Ensure that AG’s queries are attended to timeously | Ministerial Rep | 2019-09-01 | 31 November 2019 |  | Audit underway, and queries are attended to as they get raised.
MM
GMs
2.5 | Review Performance Contracts to address AG findings | Reviewed Performance contracts signed | Review performance contracts and incorporate AG findings in KPA | Ministerial Rep | 2019-09-01 | 2019-12-31 | Signed performance contracts | Not achieved..
MM
GMs
Mgr: PMS
PUBLIC PARTICIPATION
2.6 | Customer Satisfaction Survey | Undertaken a Customer Satisfaction Survey | Undertake customers quarterly to understand expectations. Develop Action List to Mitigate against Adverse Feedback Monitor Corrective Actions and give Feedback to Further Measure Appreciation thereof | Ministerial Rep | 2019-09-01 | 2019-12-31 | Quarterly Results of surveys Undertaken | Not achieved
MM
Mgr: Comm
Mgr. Mayor’s Office
2.7 | Protests | Developed Crowd Control Strategy (Protests) | Develop the Strategy based on the Analysis Outcome and Infrastructure Assessments for Basic services Link such Strategy to the Risk Management and Proactive Maintenance Plans of the District | Ministerial Rep | 2019-09-01 | 2019-12-31 | Council Approved Strategy and Risk Management Implementation Plans
MM
Mgr: Comm
Mgr. Mayor’s Office
KPA 3: SERVICE DELIVERY INTERVENTIONS
PROJECT MANAGEMENT UNIT
3.1 | Project Prioritisation | Five-Year Project Implementation Plan | Review project priority and update IDP accordingly | Ministerial Rep | 2019-09-01 | 2019-10-31 | Updated IDP | Not yet achieved
|  | (Master Plan) |  | MM
GM:WS&T
PMU Mgr
3.2. | Project Implementation Approach | Source to tap project delivery per phase | Review project phases (Multiyear projects) to prioritise Reticulation network where Bulk infrastructure phases has been completed and commissioned | Ministerial Rep | 2019-09-01 | 2019-10-31 | Updated IDP | The new approach has been discussed with the PMU managers. Projects with bulk infrastructure and funding source has been identified.
MM
GM:WS&T
PMU Mgr
3.3. | Water Source Augmentation | Uninterrupted water supply to Ladysmith and surrounding areas | Short Term Intervention: Commissioning of the Lambardskop project to supplement water supply in Ladysmith | Ministerial Rep | 2019-09-01 | 2019-10-31 | Updated IDP | Funding available for commissioning of the Lambardskop line
MM
|  |  | Medium Term: Investigate Klipriver Catchment and water license holders (from the Ingula to the Klipriver) | GM:WS&T |  |  |  | Reinstating of the Klipriver catchment forum
PMU Mgr
|  |  | Long Term: Upgrade Bulk water line from Spionkop dam (Business plan required) | Area Eng. |  |  |  | Panel of consultants appointed for population of Business Plans
3.4 |  | Increased capacity at Olifantskop Dam | Complete desilting Olifantskop dam | Ministerial Rep | 2018-07-01 | 2019-10-31 | Disilted dam | +/- 80% 200 000 m3 of silt removed to date
MM
GM:WS&T
PMU Mgr
3.5 |  | Increased water storage capacity at Loskop ponds | Excavate Loskop ponds | Ministerial Rep | 2019-09-01 | 2019-10-31 | Excavated Loskop ponds | Equipment for removal of silt procured
MM
GM:WS&T
Area Eng.
3.6 |  | Okhahlamba Bulk Water Infrastructure | Develop Business Plans for a 30 mega litre Water Treatment Works for Okhahlamba area | Ministerial Rep | 2019-09-01 | 2019-10-31 |  | Panel of consultants appointed for population of Business Plans
MM
GM:WS&T
PMU Mgr
3.7 | Capacitation of Project Management Unit (PMU) | KPIs for PMU Staff | Distribute projects equitable amongst staff to enable the monitoring of projects | Ministerial Rep | 2019-09-01 | 2019-09-30 | 100% Expenditure of trenched grants
MM
GM:WS&T
3.8 | Spending on MIG and all Other Conditional Grants | Full MIG expenditure of 1st quarter tranche | Ensure that Finance attends the MIG MIS training so as to update grant payments made | Ministerial Rep | 2019-09-01 | 2020-09-30 | 100% expenditure of tranched MIG by end of 1st quarter. | MIS Training held in September 2019
MM
MISA
OPERATIONS AND MAINTENANCE: DISTRICT-WIDE
3.9 | Refurbishment of Hand Pumps | Status report on all hand pumps | Audit and Record all faulty hand pumps and schemes | Ministerial Rep | 2018-08-01 | 2019-10-31 | Weekly reports on progress achieved | Achieved
MM
GM:WS&T
Area Eng.
3.1 |  | Refurbished Hand pumps | Develop the Ward Based Mitigation Programme and Implement such with Periodic Monitoring & Report | Ministerial Rep | 2018-08-01 | 2019-10-31 | Weekly reports on progress achieved | There is a dedicated team which operating in rural areas currently
MM
GM:WS&T
Area Eng.
3.11 | Refurbishment of Production Boreholes | Restored Production Boreholes | Develop the Ward Based Mitigation Programme and Implement such with Periodic Monitoring & Report | Ministerial Rep | 2018-08-01 | 2019-10-31 | Weekly progress reports | There is a dedicated team which operating in rural areas currently
MM
GM:WS&T
Area Eng.
3.12 | AC Pipe Replacement | New pipes | Identify old AC pipes and replace | Ministerial Rep | 2018-08-01 | 2019-10-31 | Weekly progress reports | Funding source has been identified
MM
GM:WS&T
Area Eng.
3.13 | Pump stations | Refurbished water and sewerage pump stations | Refurbish water pumps and control panels as well as sump desludging | Ministerial Rep | 2018-08-01 | 2019-10-31 | Weekly progress reports | Funding source has been identified
MM
GM:WS&T
Area Eg.
OPERATIONS AND MAINTENANCE: EKUVUKENI INTERVENTIONS
3.14 | Desilting of and hydrographic survey for Olifantskop Dam | Improved bulk water storage capacity | Facilitate the Umgeni Water undertakes ultra sound survey and capacity assessment study | Ministerial Rep | 2018-08-01 | 2019-12-31 | Fully desilted Olifantskop Dam | Umgeni water Procurement processes commenced
MM
GM:WS&T
3.15 | Feasibility study of implementation of Spieonkop Regional Bulk Water Supply Scheme project | Plans for the implementation of Spieonkop Regional Bulk Water Supply Scheme project | Facilitate the Umgeni Water undertakes Feasibility study for Spieonkop Regional Bulk Water Supply Scheme project | Ministerial Rep | 2018-08-01 | 2019-12-31 | Feasibility Study report | Not Achieved
MM
GM:WS&T
3.16 | Drilling and equipping of five (5) production Boreholes | Five (5) Equipped production boreholes | Facilitate that Umgeni Water drills and equip five (5) production boreholes | Ministerial Rep | 2018-08-01 | 2019-12-31 | Five (5) production boreholes | Boreholes drilled but discovered that there is High Fluoride and High salt contents and presence of E coli.
MM
|  |  |  | GM:WS&T |  |  |  | An alternative location for drilling needs to be identified
Or the construction of treatment works be prioritised
3.17 | New and bigger rising main from Oliphantskop Plant to Petronella reservoir. | Improved supply of water Petronella reservoir | Facilitate the completion of Petronella water supply improvement intervention | Ministerial Rep | 2018-08-01 | 2019-12-31 |  | Project underway. Project expenditure at 25%
MM
GM:WS&T
KPA 4: FINANCIAL HEALTH IMPROVEMENTS
4.1 | Unfunded Budget | Reduced expenditure on non-core business activities | Communicate the content of MFMA Circular 82 and place moratorium on non-core service delivery expenditure | Ministerial Rep | 2019-09-01 | 2019-09-30 | Communique to all staff and Councillors | Cost-driver analysis features weekly in the IFC agenda
MM
CFO
GMs
4.2 |  | All requisitions and payments actioned only once approved through the IFC | Hold weekly IFC meeting to review and approve requisitions and payments as well as annual and quarterly cash-flow statement | Ministerial Rep | 2018-08-01 | 2019-12-31 | IFC minutes | All requisitions and payments are processed through IFC
MM
CFO
GMs
4.3 |  |  | Review all contracts for contracted services | Ministerial Rep | 2018-08-01 | 2019-09-30 | Re-negotiated monthly commitments | Achieved
MM
CFO
GMs
4.4. | Payment of Long-outstanding creditors | Avoidance of litigation by creditors | Negotiate and conclude payment plans with creditors | Ministerial Rep | 2019-09-01 | 2019-12-31 | Payment Plans | Commenced with creditors owed over R1m
MM
CFO
4.5 | Data Cleansing | Dedicated project implemented to cleanse Municipal Data for accurate billing purposes | Verify and update consumer database | Ministerial Rep | 2019-09-01 | 2019-12-31 | Reduction in billing complaints | Project underway
|  |  |  | MM |  |  | Exception report
CFO
4.6 | Revenue Collection | Improved water revenue collection | Review and implement Credit Control Policy | Ministerial Rep | 2019-09-01 | 2019-12-31 | Increase in collections
MM
CFO
Mgr.: Revenue
4.7 |  | Revenue Collection strategy | Develop and implement revenue collection strategy | Ministerial Rep | 2019-09-01 | 2019-12-31 | Increase in revenue collection | Strategy developed and approved by Council.
MM, CFO
Mgr.: Revenue
Hon. Mayor
4.8 | Revenue enhancement | Revenue Enhancement strategy | Roll out meters to new middle-income settlements/developments | Ministerial Rep | 2019-09-01 | 2019-12-31 | Increased new meter installations | A request has been made to Housing project’s IAs to install pre-paid meters.
MM
CFO
4.9 |  |  | Bench-mark tariffs with other water providers | Ministerial Rep | 2019-09-01 | 2020-06-30 |  | Done. Ready for the following year’s budget. CFO already discussing possible tariff hike with the Chamber of Commerce
MM
CFO
4.1 | Conditional grants management | Compliance with grants’ conditions | Open separate banks for each grant or open a separate bank account for all conditional grants and develop and keep an up to date grant’s register. | Ministerial Rep | 2019-09-01 | 2019-12-31 | Monthly recons reports | Achieved
MM
CFO
4.11 |  |  | Create and implement Grants’ Replenishment Plan | Ministerial Rep | 2019-09-01 | 2019-12-31 | Report on the way forward produced | Plan created by not implementable due to shortage of funds
MM
CFO
4.12 | Contract Management | Eradication of unwarranted variation orders and lapses of contracts | Review all contracts timeous and terminate green contracts | Ministerial Rep | 2019-07-01 | 2020-06-30 | Audit reports | Achieved
MM
CFO
GMs
Snr Managers
4.13 | Internal Audit & AG Findings | AG’s Action plan | Address all root causes for repeat findings | Ministerial Rep | 2019-07-01 | 2020-06-30 | Council resolution and committed action to the plan | Audit process in progress
|  |  | Develop a plan for targeted improvement for the next three years | MM
CFO
GMs
Snr Managers
4.14 | Financial Reporting | Accurate, timeous and stakeholder-customised reports produced as per legislative and accounting prescripts | Identify all monthly, quarterly, mid-year and yearly reports and timeframes within which they must be produced and adhere to them | Ministerial Rep | 2019-09-01 | 2020-06-30 | Reports produced in compliance with legislation | Section 71 reports up to date now
|  |  | Ensure quality checks for all reports | MM
|  |  | Train teams on reporting requirements | CFO
GMs
4.15 | Monthly Registers for Unauthorised, Irregular, fruitless and wasteful expenditure. | Monthly reports produced to monitor UIFW | Compilation of monthly reports | Ministerial Rep | 2019-09-01 | 2020-06-30 | Monthly registers signed off by MM | Achieved. The register exists
|  |  | Submission of reports to oversight committees | MM
CFO
4.16 | Fleet management | Fleet replacement plan developed | Fleet needs analysis undertaken | Ministerial Rep | 2019-09-01 | 2019-12-30 | Plan approved by Council | Underway
|  |  | Plan developed | MM
|  |  | Funding alternatives developed | GMs
4.17 |  | Monthly reports produced on fleet abuses and consequence management implemented and monitored | Prevent abuse of fleet | GMs | 2019-09-01 | 2019-12-30 | Monthly report produced for MM’s and IFC’s attention and quarterly presented to Finance Committee, Audit Committee and MPAC | Not yet achieved
|  |  | Monitor daily usage of fleet and fuel | Snr Managers
Managers
Supervisors
KPA 5: ECONOMIC DEVELOPMENT AND PLANNING
5.1 | Long-Term Economic Development Strategy | Long-term economic development plan developed | Undertake an analysis of competitive advantages | Ministerial Rep | 2019-07-01 | 2020-06-30 | Plan approved by Council | Not commenced yet
|  |  | Review bottlenecks to economic development | MM
|  |  | Identify catalytic projects for implementation | GM: SD
5.2 | SMME Support | Developed & Implemented Emerging Contractor Development Strategy & Programmes | Review SCM Policy to allow for Empowerment of Locally Based Enterprises and create a database/ panel of Enterprises as part of a Developed Programme | Ministerial Rep | 2019-09-01 | 2020-12-31 | Plan approved by Council | Not yet achieved
MM
CFO
All SMgrs
Uthukela Recovery Plan as at 19 September 2019
Focus Area/KPA | Remedial Actions | Targets | Targets | Comment/Reasons for Deviation
|  | met | not met
|  | Sep’19 | Sep’19
1. Good Governance & Public Participation (B2B Pillar 3: Good Governance and B2B Pillar 1: Putting People First) | 8 | 0 | 0
2. Municipal Financial Viability (B2B Pillar 4: Sound Financial Management) | 17 | 0 | 0
3. Institutional Development & Municipal Transformation (B2B Pillar 5: Building Institutional Capabilities, B2B Pillar 3: Good Governance and B2B Pillar 1: Putting People First) | 7 | 0 | 0
4. Basic Service Delivery and Infrastructure (B2B Pillar 2: Delivering Basic Services) | 17 | 0 | 0
5. Local Economic Development (B2B Pillar 2: Delivering Basic Services, B2B Pillar 5: Building Institutional Capabilities, B2B Pillar 3: Good Governance and B2B Pillar 1: Putting People First) | 2 | 0 | 0
TOTAL | 51 | 0 | 0

## Financial Impact
Uthukela District Municipality: KZN_DC23
Financial Impact of the Financial Recovery Plan
No | Strategy | Focus Area | Key Activities | Actions taken |  | Draft | Key Activities
|  |  |  | to reduce expenditure | 2019 Actual | 2021 Budget | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
1 | Minimise consultants to essential only | professional fees | complete transfer of skills to permarnent employees | The municipality had previously cut off all consultants fro the budget. Hoewver there are a few areas where they could not be eliminated, job evaluation, asset management. | -4373817 | 900894.5 | 3472922.5 | 3632676.935 | 3828841.4895 | 4004968.198 | 4189196.7351 | 4381899.7849 | 4583467.175 | 4794306.6651 | 5014844.7717 | 5245527.6312
2 | Reduce Security cost | security | Review the number of security guards on plants | Mayors bodyguards have been reduced. The number of security guards at plants have been reduced. uMngeni Water will now pay for their own security at the plants transferred to them. The municipality is currently out of tender for security and budget constraints will be the key factor in the appointment of a service provider. | -25241556 | 20496961.255 | 4744594.745 | 4962846.1033 | 5230839.7928 | 5471458.4233 | 5723145.5108 | 5986410.2043 | 6261785.0737 | 6549827.1871 | 6851119.2377 | 7166270.7226
|  | uMngeni recovery of security cost |  |  |  | -1232769.576 | 1232769.576 | 1289476.9765 | 1359108.7332 | 1421627.735 | 1487022.6108 | 1555425.6509 | 1626975.2308 | 1701816.0914 | 1780099.6316 | 1861984.2147
3 | Reduce Legal fees | legal fees | Reduce legal letigations against the municipality | the municipality had taken a stance of complete eliminating legal fees from the budget, however there are litigations which cannot be handled internally. The budget also includes an amount for the publication of by-laws. | -3977158 | 2500000 | 1477158 | 1545107.268 | 1628543.0605 | 1703456.0413 | 1781815.0192 | 1863778.51 | 1949512.3215 | 2039189.8883 | 2132992.6231 | 2231110.2838
4 | Reprioritise mantainance and refurbishment of assets | Repairs to pumps and Pipelines | Utilise a portion of grant funding for the refurbishment of assets, transfer plants to uMngeni water | uMngeni Water will take over the responsibility of refurbishing the plants transferred to them. The capital grants will be divertered towards the refurdbishmnet of capital infrastructure. | -15296066 | 7337511.1078 | 7958554.8922 | 8324648.4172 | 8774179.4317 | 9177791.6856 | 9599970.1031 | 10041568.7279 | 10503480.8893 | 10986641.0102 | 11492026.4967 | 12020659.7156
5 | Reduce repairs to vehicles | vehicles | buy new vehicles, | The municipality is exploring all avenues to replace existing aged fleet. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | create a panel of service providers to acquire competitive prices, use of internal mechanic outsource parts only | Mechanic has been employed to do repairs internally. A panel of service providers has been created through the appropriate SCM processes. | -8610530 | 8882500 | -271970 | -284480.62 | -299842.5735 | -313635.3319 | -328062.5571 | -343153.4348 | -358938.4928 | -375449.6634 | -392720.3479 | -410785.4839
6 | Reduce amount spent on protective clothing | protective clothing | review protective clothing policy, limit procured items to essential protective clothing for qualifying employees only | Policy has been reviewed and will be submitted to Council for adoption during January 2020 (Draft policy attached). The cost containment restrictions on this expenditure item was not well received by employees management continues to engage with the LLF and will review final budget amount. | -2183264 | 3000000 | -816736 | -854305.856 | -900438.3722 | -941858.5373 | -985184.0301 | -1030502.4954 | -1077905.6102 | -1127489.2683 | -1179353.7747 | -1233604.0483
7 | Reduce amount spent on telephones, cell phones and fax | telecommunication | review cell phone eligibilty of employees, reduce cellphone and data limits, reduce telephone use to qulitying employees and recover any amount for personal use, port cell phones to MTN and acquire cheaper standard cellphones | All listed actions have been implimented to reduce expenditure on telecommunication. | -2980241 | 2295434 | 684807 | 716308.122 | 754988.7606 | 789718.2436 | 826045.2828 | 864043.3658 | 903789.3606 | 945363.6712 | 988850.4001 | 1034337.5185
8 | Reduce the hire of vihicles and plant | vehicle hire | no budget for the hire of vehicles for office bearers in the event of vehicle breakdown | No vehicles has been hired to date. Completely eliminated from the budget. | -210000 | 0 | 210000 | 219660 | 231521.64 | 242171.6354 | 253311.5307 | 264963.8611 | 277152.1987 | 289901.1998 | 303236.655 | 317185.5412
|  | plant hire | reduce the number of hours used for hired plants, and rotate the use of municipal owned plant, repair municipal ownwed plant. | The number of hours for the procurement of plant hire has been reduced. The Mechanic appointed is repairing and maintaining municipal owned plant. Municipal plant is being rotated as and when required. | -4024225 | 2403500 | 1620725 | 1695278.35 | 1786823.3809 | 1869017.2564 | 1954992.0502 | 2044921.6845 | 2138988.082 | 2237381.5338 | 2340301.0843 | 2447954.9342
9 | Reduce the amount spent on comsumables such as cleaning materials | consumables | monitor the use of cleaning materials and other consumables such as tissue paper, increases control procedures at stores | Departmental access to stores has been restricted by SCM. Consumables are released using newly developed job cards. | -526778 | 200000 | 326778 | 341809.788 | 360267.5166 | 376839.8223 | 394174.4541 | 412306.479 | 431272.5771 | 451111.1156 | 471862.2269 | 493567.8894
10 | Overtime |  |  | Job cards have been developed to monitor and restrict overtime. Employees earning above treshhold don’t get paidovertime . The eligibility of employees to receive standby allowance has been reviewed. | -26620146 | 15000000 | 11620146 | 12154672.716 | 12811025.0427 | 13400332.1946 | 14016747.4756 | 14661517.8595 | 15335947.681 | 16041401.2743 | 16779305.7329 | 17551153.7967
11 | Fuel and Oil | Fleet management | Prevent abuse of fleet.Monitor daily usage of fleet and fuel. Fleet management plan attached | All drivers has been issued with a computer tag. Vehicles can only refuel with the tag. Service provider has been appointed to produce monhly reports on fuel and oil usage which will eliminate fraude. | -13758713 | 6897000 | 6861713 | 7177351.798 | 7564928.7951 | 7912915.5197 | 8276909.6336 | 8657647.4767 | 9055899.2606 | 9472470.6266 | 9908204.2755 | 10363981.6721
12 | Reduce the amount spent on advertising | advertising | reduced budget for radio slots and event advertising. | All listed actions have been implemented | -433106 | 200000 | 233106 | 243828.876 | 256995.6353 | 268817.4345 | 281183.0365 | 294117.4562 | 307646.8592 | 321798.6147 | 336601.351 | 352085.0131
[5 empty] | -108235600 | 68881031.2868 | 39354568.7132 | 41164878.874 | 43387782.3331 | 45383620.3205 | 47471266.8552 | 49654945.1306 | 51939072.6066 | 54328269.9465 | 56827370.364 | 59441429.4007

## Table A4_B4
Uthukela District Municipality: KZN_DC23
Financial Impact of the Financial Recovery Plan on the Financial Performance (Table A4/B4)
Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
R thousand | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Revenue By Source
Property rates
Service charges - electricity revenue
Service charges - water revenue | 265271856.632 | 277474362.0371 | 290238182.6908 | 303589139.0946 | 317554239.4929 | 332161734.5096 | 347441174.297 | 363423468.3147 | 380140947.8572 | 397627431.4586
Service charges - sanitation revenue | 17979192 | 18806234.832 | 19671321.6343 | 20576202.4294 | 21522707.7412 | 22512752.2973 | 23548338.903 | 24631562.4925 | 25764614.3672 | 26949786.6281
Service charges - refuse revenue |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rental of facilities and equipment |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest earned - external investments | 6097260.2496 | 6377734.221 | 6671109.9952 | 6977981.055 | 7298968.1835 | 7634720.72 | 7985917.8731 | 8353270.0952 | 8737520.5196 | 9139446.4635
Interest earned - outstanding debtors | 68673768 | 71832761.328 | 75137068.3491 | 78593373.4931 | 82208668.6738 | 85990267.4328 | 89945819.7347 | 94083327.4425 | 98411160.5049 | 102938073.8881
Dividends received |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fines, penalties and forfeits |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Licences and permits |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Agency services |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transfers and subsidies | 481218000 | 514234000 | 551419058 | 576784334.668 | 603316414.0627 | 631068969.1096 | 660098141.6887 | 690462656.2063 | 722223938.3918 | 755446239.5578
Other revenue | 26575068.773 | 27797523.2126 | 29076209.8323 | 30413715.4846 | 31812746.3969 | 33276132.7312 | 34806834.8368 | 36407949.2393 | 38082714.9043 | 39834519.7899
Gains on disposal of PPE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue (excluding capital transfers and contributions) | 865815145.6546 | 916522615.6307 | 972212950.5017 | 1016934746.2248 | 1063713744.5511 | 1112644576.8004 | 1163826227.3333 | 1217362233.7906 | 1273360896.545 | 1331935497.786
Expenditure By Type
Employee related costs | 312770980.3125 | 327158445.4069 | 342207733.8956 | 357949289.6548 | 374414956.9789 | 391638044.9999 | 409653395.0699 | 428497451.2432 | 448208334.0003 | 468825917.3644
Remuneration of councillors | 6371543 | 6664633.978 | 6971207.141 | 7291882.6695 | 7627309.2723 | 7978165.4988 | 8345161.1117 | 8729038.5229 | 9130574.2949 | 9550580.7125
Debt impairment | 175709349 | 183791979.054 | 192246410.0905 | 201089744.9546 | 210339873.2226 | 220015507.3908 | 230136220.7308 | 240722486.8844 | 251795721.2811 | 263378324.46
Depreciation & asset impairment | 61048441.476 | 63856669.7839 | 66794076.594 | 69866604.1173 | 73080467.9067 | 76442169.4304 | 79958509.2242 | 83636600.6485 | 87483884.2783 | 91508142.9551
Finance charges | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bulk purchases | 136845642.56 | 143140542.1178 | 149725007.0552 | 156612357.3797 | 163816525.8192 | 171352086.0069 | 179234281.9632 | 187479058.9335 | 196103095.6444 | 205123838.0441
Other materials | 14561641.8857 | 15231476.9905 | 15932125.3901 | 16665003.158 | 17431593.3033 | 18233446.5953 | 19072185.1386 | 19949505.655 | 20867182.9151 | 21827073.3292
Contracted services | 69806489.6133 | 71855231.7764 | 75191810.4381 | 78650633.7182 | 82268562.8693 | 86052916.7613 | 90011350.9323 | 94151873.0752 | 98482859.2366 | 103013070.7615
Transfers and subsidies | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other expenditure | 88701057.807 | 91606768.4661 | 95590679.8156 | 99987851.0871 | 104587292.2371 | 109398307.68 | 114430629.8333 | 119694438.8056 | 125200382.9907 | 130959600.6082
Loss on disposal of PPE
Total Expenditure | 865815145.6546 | 903305747.5736 | 944659050.4199 | 988113366.7393 | 1033566581.6093 | 1081110644.3633 | 1130841734.004 | 1182860453.7682 | 1237272034.6415 | 1294186548.235
Surplus/(Deficit) | 0 | 13216868.0571 | 27553900.0817 | 28821379.4855 | 30147162.9418 | 31533932.4372 | 32984493.3293 | 34501780.0224 | 36088861.9034 | 37748949.551

## Table A5_B5
Uthukela District Municipality: KZN_DC23
Financial Impact of the Financial Recovery Plan on the Capital Financial Performance (Table A5/B5)
Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
R thousand | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Capital Expenditure - Functional
Governance and administration
Executive and council
Finance and administration
Internal audit
Community and public safety
Community and social services
Sport and recreation
Public safety
Housing
Health
Economic and environmental services
Planning and development
Road transport
Environmental protection
Trading services
Energy sources
Water management | 307046000 | 389299000 | 437283000 | 457398018 | 478438326.828 | 500446489.8621 | 523467028.3957 | 547546511.7019 | 572733651.2402 | 599079399.1973
Waste water management
Waste management
Other
Total Capital Expenditure - Functional | 307046000 | 389299000 | 437283000 | 457398018 | 478438326.828 | 500446489.8621 | 523467028.3957 | 547546511.7019 | 572733651.2402 | 599079399.1973
Funded by:
National Government | 307046000 | 389299000 | 437283000 | 457398018 | 478438326.828 | 500446489.8621 | 523467028.3957 | 547546511.7019 | 572733651.2402 | 599079399.1973
Provincial Government
District Municipality
Other transfers and grants
Transfers recognised - capital
Borrowing
Internally generated funds
Total Capital Funding | 313937000 | 442806000 | 704719420 | 742774268.68 | 782884079.1887 | 825159819.4649 | 869718449.716 | 916683246.0007 | 966184141.2847 | 1018358084.9141

## Table A6_B6
Uthukela District Municipality: KZN_DC23
Financial Impact of the Financial Recovery Plan on the Financial Position (Table A6/B6)
Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
R thousand | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
ASSETS
Current assets
Cash | 10887725.8612 | 26773438.1726 | 59418949.2504 | 242367970.4713 | 205497492.6496 | 248745179.4967 | 294118900.1798 | 341723830.8282 | 391670384.1164 | 444074471.6605
Call investment deposits | Year 2: 50000000; Year 3: 100000000
Consumer debtors | 280781441.361 | 287334462.7578 | 294188922.5255 | 307721612.9617 | 321876807.158 | 336683140.2872 | 352170564.7404 | 368370410.7185 | 385315449.6115 | 403039960.2937
Other debtors | 4329435 | 4528589.01 | 4736904.1045 | 4954801.6933 | 5182722.5712 | 5421127.8094 | 5670499.6887 | 5931342.6743 | 6204184.4374 | 6489576.9215
Current portion of long-term receivables | Year 1: 0
Inventory | 6895000 | 6895000 | 6895000 | 7212170 | 7543929.82 | 7890950.5917 | 8253934.3189 | 8633615.2976 | 9030761.6013 | 9446176.635
Total current assets | 302893602.2222 | 375531489.9404 | 465239775.8804 | 562256555.1262 | 540100952.1987 | 598740398.1851 | 660213898.9278 | 724659199.5186 | 792220779.7666 | 863050185.5106
Non current assets
Long-term receivables | 6532117.35 | 6832594.7481 | 7146894.1065 | 7475651.2354 | 7819531.1922 | 8179229.6271 | 8555474.1899 | 8949026.0027 | 9360681.1988 | 9791272.5339
Investments | Year 1: 0
Investment property | Year 1: 0
Investment in Associate | Year 1: 0
Property, plant and equipment | 3135558100.8654 | 3522048872.5575 | 3956394465.7474 | 4138388611.1718 | 4328754487.2857 | 4527877193.7008 | 4736159544.6111 | 4954022883.6632 | 5181907936.3117 | 5420275701.382
Biological | Year 1: 0
Intangible | 522500 | 546535 | 571675.61 | 597972.6881 | 625479.4317 | 654251.4856 | 684347.0539 | 715827.0184 | 748755.0612 | 783197.794
Other non-current assets | 2532035 | 2648508.61 | 2770340.0061 | 2897775.6463 | 3031073.3261 | 3170502.6991 | 3316345.8232 | 3468897.7311 | 3628467.0267 | 3795376.51
Total non current assets | 3145144753.2154 | 3532076510.9156 | 3966883375.47 | 4149360010.7416 | 4340230571.2357 | 4539881177.5125 | 4748715711.6781 | 4967156634.4153 | 5195645839.5984 | 5434645548.2199
TOTAL ASSETS | 3448038355.4375 | 3907608000.8559 | 4432123151.3504 | 4711616565.8678 | 4880331523.4344 | 5138621575.6976 | 5408929610.6059 | 5691815833.934 | 5987866619.365 | 6297695733.7305
LIABILITIES
Current liabilities
Bank overdraft
Borrowing
Consumer deposits | 33440000 | 34978240 | 36587239.04 | 38270252.0358 | 40030683.6295 | 41872095.0764 | 43798211.45 | 45812929.1767 | 47920323.9188 | 50124658.8191
Trade and other payables | 177566230 | 177566230 | 177566230 | 177566230 | 177566230 | 177566230 | 177566230 | 177566230 | 177566230 | 185734276.58
Provisions | 23428900 | 24506629.4 | 25633934.3524 | 26813095.3326 | 28046497.7179 | 29336636.6129 | 30686121.8971 | 32097683.5044 | 33574176.9456 | 35118589.0851
Total current liabilities | 234435130 | 237051099.4 | 239787403.3924 | 242649577.3685 | 245643411.3474 | 248774961.6894 | 252050563.3471 | 255476842.6811 | 259060730.8644 | 273050010.3311
Non current liabilities
Borrowing
Provisions | 39125500 | 40925273 | 42807835.558 | 44776995.9937 | 46836737.8094 | 48991227.7486 | 51244824.225 | 53602086.1394 | 56067782.1018 | 59095442.3353
Total non current liabilities | 39125500 | 40925273 | 42807835.558 | 44776995.9937 | 46836737.8094 | 48991227.7486 | 51244824.225 | 53602086.1394 | 56067782.1018 | 59095442.3353
TOTAL LIABILITIES | 273560630 | 277976372.4 | 282595238.9504 | 287426573.3621 | 292480149.1568 | 297766189.438 | 303295387.5721 | 309078928.8205 | 315128512.9662 | 332145452.6664
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
NET ASSETS | 3174477725.4375 | 3629631628.4559 | 4149527912.4 | 4424189992.5057 | 4587851374.2776 | 4840855386.2597 | 5105634223.0338 | 5382736905.1135 | 5672738106.3988 | 5965550281.0642
COMMUNITY WEALTH/EQUITY
Accumulated Surplus/(Deficit) | 3174477725.4375 | 3629631628.4559 | 4149527912.4 | 4424189992.5057 | 4587851374.2776 | 4840855386.2597 | 5105634223.0338 | 5382736905.1135 | 5672738106.3988 | 5979065964.1443
Reserves | Year 1: 0; Year 2: 0; Year 3: 0
TOTAL COMMUNITY WEALTH/EQUITY | 3174477725.4375 | 3629631628.4559 | 4149527912.4 | 4424189992.5057 | 4587851374.2776 | 4840855386.2597 | 5105634223.0338 | 5382736905.1135 | 5672738106.3988 | 5979065964.1443

## Table A7_B7
Uthukela District Municipality: KZN_DC23
Financial Impact of the Financial Recovery Plan on the Cash Flow (Table A7/B7)
Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
R thousand | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
CASH FLOW FROM OPERATING ACTIVITIES
Receipts
Property rates
Service charges | 169950629.1792 | 177768358.1214 | 185945702.595 | 194499204.9144 | 203446168.3405 | 212804692.0841 | 222593707.92 | 232833018.4843 | 243543337.3346 | 254746330.852
Other revenue | 26575069.423 | 27797522.6165 | 29076208.6568 | 30413714.255 | 31812745.1108 | 33276131.3859 | 34806833.4296 | 36407947.7674 | 38082713.3647 | 39834518.1794
Government - operating | 481218000 | 514234000 | 551419058 | 576784334.668 | 603316414.0627 | 631068969.1096 | 660098141.6887 | 690462656.2063 | 722223938.3918 | 755446239.5578
Government - capital | 307046000 | 389299000 | 437283000 | 457398018 | 478438326.828 | 500446489.8621 | 523467028.3957 | 547546511.7019 | 572733651.2402 | 599079399.1973
Interest | 6097260.2496 | 6377734.221 | 6671109.9952 | 6977981.055 | 7298968.1835 | 7634720.72 | 7985917.8731 | 8353270.0952 | 8737520.5196 | 9139446.4635
Dividends | Year 1: 0
Payments
Suppliers and employees | -709057355.1786 | -662142299.1576 | -692402082.9189 | -724252578.7331 | -757568197.3549 | -792416334.4332 | -828867485.8171 | -866995390.1647 | -906877178.1123 | -948593528.3054
Finance charges
Transfers and Grants
NET CASH FROM/(USED) OPERATING ACTIVITIES | 281829603.6732 | 453334315.8013 | 517992996.3282 | 541820674.1593 | 566744425.1706 | 592814668.7285 | 620084143.49 | 648608014.0905 | 678443982.7387 | 709652405.9447
CASH FLOWS FROM INVESTING ACTIVITIES
Receipts
Proceeds on disposal of PPE
Decrease (Increase) in non-current debtors
Decrease (increase) other non-current receivables
Decrease (increase) in non-current investments
Payments
Capital assets | -307046000 | -389299000 | -437283000 | -457398018 | -478438326.828 | -500446489.8621 | -523467028.3957 | -547546511.7019 | -572733651.2402 | -599079399.1973
NET CASH FROM/(USED) INVESTING ACTIVITIES | -307046000 | -389299000 | -437283000 | -460896282 | -485784681.228 | -512017054.0143 | -539665974.9311 | -568807937.5774 | -599523566.2065 | -631897838.7817
CASH FLOWS FROM FINANCING ACTIVITIES
Receipts
Short term loans | Year 1: 0
Borrowing long term/refinancing | Year 1: 0
Increase (decrease) in consumer deposits | 1769021.5202 | 1850396.5101 | 1935514.7496 | 2024548.4281 | 2117677.6558 | 2215090.8279 | 2316985.006 | 2423566.3163 | 2535050.3668 | 2651662.6837
Payments
Repayment of borrowing | Year 1: 0
NET CASH FROM/(USED) FINANCING ACTIVITIES | 1769021.5202 | 1850396.5101 | 1935514.7496 | 2024548.4281 | 2117677.6558 | 2215090.8279 | 2316985.006 | 2423566.3163 | 2535050.3668 | 2651662.6837
NET INCREASE/ (DECREASE) IN CASH HELD | -23447374.8066 | 65885712.3115 | 82645511.0778 | 82948940.5874 | 83077421.5984 | 83012705.5421 | 82735153.5649 | 82223642.8294 | 81455466.899 | 80406229.8467
Cash/cash equivalents at the year begin: | 34335181.3013 | 10887806.4947 | 76773518.8061 | 159419029.8839 | 122420071.0512 | 165732473.9546 | 211383746.6149 | 259500187.9988 | 310214917.2174 | 363668241.8138
Cash/cash equivalents at the year end: | 10887806.4947 | 76773518.8061 | 159419029.8839 | 242367970.4713 | 205497492.6496 | 248745179.4967 | 294118900.1798 | 341723830.8282 | 391670384.1164 | 444074471.6605

## Table A8_B8
Uthukela District Municipality: KZN_DC23
Financial Impact of the Financial Recovery Plan on the Cash backed reserves/accumulated surplus (Table A8/B8)
Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
R thousand | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Cash and investments available
Cash/cash equivalents at the year end | 10887806.4947 | 76773518.8061 | 159419029.8839 | 242367970.4713 | 205497492.6496 | 248745179.4967 | 294118900.1798 | 341723830.8282 | 391670384.1164 | 444074471.6605
Other current investments > 90 days
Non current assets - Investments
Cash and investments available: | 10887806.4947 | 76773518.8061 | 159419029.8839 | 242367970.4713 | 205497492.6496 | 248745179.4967 | 294118900.1798 | 341723830.8282 | 391670384.1164 | 444074471.6605
Application of cash and investments
Unspent conditional transfers
Unspent borrowing | Year 1: 0
Statutory requirements | 67940000 | 71065240 | 74334241.04 | 77753616.1278 | 81330282.4697 | 85071475.4633 | 88984763.3346 | 93078062.448 | 97359653.3206 | 101838197.3734
Other working capital requirements | 26138230 | 22476230 | 18646230 | 11336038.5675 | 3689449.7616 | -4308882 | -12675137 | -21426240 | -30579893 | -40154615
Other provisions | 23631000 | 24718026 | 25855055.196 | 27044387.735 | 28288429.5708 | 29589697.3311 | 30950823.4083 | 32374561.2851 | 33863791.1042 | 35421525.495
Long term investments committed | Year 1: 0; Year 2: 0; Year 3: 0
Reserves to be backed by cash/investments | Year 1: 0; Year 2: 0; Year 3: 0
Total Application of cash and investments: | 117709230 | 118259496 | 118835526.236 | 116134042.4304 | 113308161.8022 | 110352290.7944 | 107260449.743 | 104026383.7331 | 100643551.4249 | 97105107.8684
Surplus(shortfall) | -106821423.5053 | -41485977.1939 | 40583503.6479 | 126233928.0409 | 92189330.8474 | 138392888.7023 | 186858450.4368 | 237697447.0951 | 291026832.6915 | 346969363.7921

## Calc.other working capital
Uthukela District Municipality: KZN_DC23
Financial Impact of the Financial Recovery Plan on the Cash backed reserves/accumulated surplus (Table A8/B8)
Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
R thousand | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Net Debtors | 291642993.711 | 298695646.5159 | 306072720.7365 | 320152065.8904 | 334879060.9214 | 350283497.7237 | 366396538.619 | 383250779.3955 | 400880315.2477 | 419320809.7491
Collection Rate as per A8 | 51.92% | 51.92% | 51.92% | 51.92% | 51.92% | 51.92% | 51.92% | 51.92% | 51.92% | 51.92%
Debtors | 151427636.5504 | 155089533.3513 | 158919877.0865 | 166230191.4325 | 173876780.2384 | 181875112.1293 | 190241367.2873 | 198992470.1825 | 208146123.8109 | 217720845.5062
Credtiors | 177566230 | 177566230 | 177566230 | 177566230 | 177566230 | 177566230 | 177566230 | 177566230 | 177566230 | 177566230
Other working capital | -26138593.4496 | -22476696.6487 | -18646352.9135 | -11336038.5675 | -3689449.7616 | 4308882.1293 | 12675137.2873 | 21426240.1825 | 30579893.8109 | 40154615.5062