## Sheet1
IDP Project Summary Report - 2019/20 IDP projects and roll overs from prior years |  | 2019/20 IDP PROJECT TO BE INCLUDED IN THE 2020/21 | [13 empty] | ANNEXURE 5 | [8 empty] | ANNEXURE C
Vote Number | PROJ NO | PROJECT NAME | DEPARTMENT | PROJ YEAR | Operating | Capital | 2018/19 Roll Over | 2019/20 IDP | 2019/20 Adjustments | 2019/20 IDP | 2020/21 IDP | Capital/Opex | Approved Budget 2019/20 | Actual 19/20 | Projections | Proposed Rollover to 2020/21 Budget | Remaining | Adjustment | Adjusted Budget | PAID 17/18 YEAR | REMAINING | Savings / Transfers | Date paid | RESP MAN | Comment | Roll over 20/21 | Draft Adjusted Budget
| 1 | Municipal Environmental Health & Environmental Management
009/015174 | EHM011 | Stack Monitoring Equipment | SDCS | 2020 |  | 300000 | 0 | 300000 | 0 | 0 | 0 | Capex | 300000 | 4513.3565 | 0 | 295486.6435 | 295486.6435 | [7 empty] | The pricing were higher than the budgeted amount of the project. The number of equipments were scaled down and the project was going for re-advertisement before lockdown due to COVID 19 Pandemic |  | 300000
008/015174 | EHM012 | Instant Sampling Kits for food and water | SDCS | 2020 |  | 500000 | 0 | 500000 |  |  |  | Capex | 500000 | 4513.0435 | 0 | 495486.9565 | 495486.9565 | [7 empty] | All the bidders did not meet the requirement. The project was going to be re- advertised and due to lockdown the project was not asdvertised. | roll over | #VALUE!
[5 empty] | 0 | 800000 | 0 | 800000 | 0 | 0 | 0 |  | 800000 | 9026.4 | 0 | 790973.6 | 790973.6 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | 0 | #VALUE!
0
| 2 | Disaster Management: Fire Fighting
008/015174 | DM0 17 | Procurement of Red Fleet | Disaster | 2020 |  |  | 19452015 |  |  |  |  | Roll-over | 19452015 | 14468340 | 4983675 | 4983675 | 4983675 | [7 empty] | On Tuesday, 26 May 2020 there was an inspection conducted.The project is currently at 98 % complete, only additional equipment and tools must be installed after arrival at the service provider. The project was badly affected by the COVID-19 lockdown and anticipate to complete all work within this 2019/20 financial year. |  | 19452015
[7 empty] | 19452015 | 0 | 0 | 0 | 0 | 0 | 19452015 | 14468340 | 4983675 | 4983675 | 4983675
| 3 | Local Economic Development & Tourism
004/015174 | UE037 | Review of SDF | PED | 2020 | 700000 |  | 0 | 350000 | 450000 |  |  | Opex | 800000 | 0 | 0 | 800000 | 800000 | [6 empty] | PED | There is a need for renewed supply chain management (SCM) processes i.e.; re-advert for Service Provider(s), tender evaluations, selection and awarding. The expenditure for SDF review has been delays due to Covid-19 impact. Alternatively we can appoint one of the previously evaluated bidders. | Rollover | #VALUE!
[5 empty] | 700000 | 0 | 0 | 350000 | 450000 | 0 | 0 |  | 800000 | 0 | 0 | 800000 | 800000 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | 0 | #VALUE!
| 4 | Roads & Storm Water
| RS048 | MIG - Development Park Ward 7 |  | 2019 | [19 empty] | ID
| RS047 | MIG - Phagameng Treets and Stormwater |  | 2019 | [19 empty] | ID
| RS046 | MIG - Paving of streets Leseding |  | 2019 | [19 empty] | ID
| RS049 | MIG - PMU Overhads |  | 2019 | [19 empty] | ID
| RS050 | Thabazimbi Waste Mamagement treatment |  | 2019 | [19 empty] | ID
003/015174 | RS047 | Planning, design, documentation, refurbishment and monitoring of WDM | ID | 2020 |  | 7000000 | 0 | 1028000 | -400000 |  |  | Capex | 628000 | 0 | 0 | 628000 | 628000 | [7 empty] | The project awaits appointment for panel of professional service provider.The process was affected by covid 19 lockdown however evaluations and adjudjications where completed. The appointment letter was sent to service provider prior to lockdown 5. | Roll over | #VALUE!
[5 empty] | 0 | 7000000 | 0 | 1028000 | -400000 | 0 | 0 |  | 628000 | 0 | 0 | 628000 | 628000 | 0 | 1 | 0 | #REF! | 0 |  |  |  | 0 | #VALUE!
| 5 | Municipal Support & Institutional Development
003/015174 | IN019 | Work Study | CSSS | 2019 | 0 |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 |  | #REF! |  | #REF! |  |  | CSSS
003/015174 | IN048 | Job Evaluation | CSSS | 2019 |  |  | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 |  | #REF! |  | #REF! |  |  | CSSS
003/015174 | IN050 | Municipal Systems Improvement Grant | CSSS | 2019 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | #REF! |  | #REF! |  |  | BTO
003/015174 | IN022 | Office Furniture | CSSS | 2020 |  | 1500000 | 0 | 250000 | 150000 |  |  |  | 400000 | 163990 | 0 | 236010 | 236010 | [7 empty] | Project will be defferred to the next financial year due to Covid-19 | Roll over
003/015174 | IN023 | Fleet Management System | CSSS | 2020 | 1000000 |  | 0 | 250000 | -250000 | 0 | 0 |  | 1000000 | 0 | 0 | 1000000 | 1000000 | [7 empty] | Project will be defferred to the next financial year due to Covid-19 | Roll over
003/015174 | IN026 | Disaster Recovery Solution | CSSS | 2020 | 0 | 2000000 | 0 | 1000000 | 999996 |  |  |  | 2000000 | 0 | 0 | 2000000 | 2000000 | [7 empty] | Project will be defferred to the next financial year due to Covid-19 | Roll over
[5 empty] | 1000000 | 3500000 | 0 | 1500000 | 899996 | 0 | 0 |  | 3400000 | 163990 | 0 | 3236010 | 3236010 | 0 | #REF! | 0 | #REF! | 0 |  |  |  | 0 | 0
| 7 | Land
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
| 8 | Sports, Arts & Culture
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
| 9 | Water & Sanitation
| WA001 | Mabatlane EXT 6 Network for 300 Erven |  | 2019 | #REF! | [13 empty] | #REF! |  | #REF! |  |  | ID
| WA002 | Mabatlane Drill, Test & Equip Boreholes |  | 2019 | #REF! | [13 empty] | #REF! |  | #REF! |  |  | ID
| WA003 | Phagameng Ext 13: install skeleton network for 1300 erven |  | 2019 | #REF! | [13 empty] | #REF! |  | #REF! |  |  | ID
| WA005 | Mabaleng Storage 1.5 MI pressure tower |  | 2019 | #REF! | [13 empty] | #REF! |  | #REF! |  |  | ID
| WA007 | Mookgophong: install valves, PRVs and chambers in existing network |  | 2019 | #REF! | [13 empty] | #REF! |  | #REF! |  |  | ID
| WA008 | Roedtan : Drill & Equip additional Boreholes and upgrade network |  | 2019 | #REF! | [13 empty] | #REF! |  | #REF! |  |  | ID
| WA0012 | Development of groundwater for Thabazimbi and Regorogile |  | 2019 | #REF! | [13 empty] | #REF! |  | #REF! |  |  | ID
| WA0013 | Schillpadnek(Smasherblock) Water supply |  | 2019 | #REF! | [13 empty] | #REF! |  | #REF! |  |  | ID
| WA0014 | Raphuti/Leeupoort water supply |  | 2019 | #REF! | [13 empty] | #REF! |  | #REF! |  |  | ID
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | #REF! | 0 | #REF! | 0
| 10 | Electricity
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
| 11 | Transport
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 25080015 | 14641356.4 | 4983675 | 10438658.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF!
|  | TOTAL APPROVED BUDGET | [10 empty] | 25080015
|  | TOTAL SPENT UP TO 30 APRIL 2020 | [10 empty] | 14641356.4
|  | ACTUAL % SPENT | [10 empty] | 58.38%
TOTAL Approved budget
|  | Capx |  |  |  |  | 10328000
|  | Project Expenditure (included in Opex) |  |  |  |  | 9132340
|  | Roll-overs |  |  |  |  | #REF!
|  | Total |  |  |  |  | #REF!