## Summary
Consolidated information for all metros
Statistical indicators on service delivery as at the beginning of 2016/17 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service | 835454 | Sites
|  | Number of households living in informal settlements | 626763 | Households
|  | Number of hectares of land already acquired and suitable for human settlements development | 50 | hectares
|  | Number of households in formal areas with access to basic electricity | 1844792 | Households
|  | Number of households living in informal areas with access to basic electricity | 0 | Households
|  | Number of households in formal areas receiving water services | 1018038.279 | Households
|  | Number of households living in informal areas receiving water services | 381064 | Households
|  | Number of households in formal areas receiving sewerage services | 1279491.876 | Households
|  | Number of households living in informal areas receiving sewerage services | 303924 | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) | 1260999 | Households
|  | Number of households living in informal areas with access to refuse removal | 622960 | Households
QUARTERLY PERFORMANCE REPORTS - 2016/17
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2016/17 | Target for 2016/17 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2016/17. | Actual output for 2016/17 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 | 270 | 170 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 120 | 0 | -120 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 | 48709 | 745 | 384 | 45 | 0 | 45 | 0 | 45 | 0 | 880 | 384 | 0 | -384 | TRUE
| Percentage density reduction in total informal settlements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 | 12 | 2 | 2 | 2 | 0 | 2 | 0 | 3 | 0 | 9 | 2 | 0 | -2 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 | 8200 | 2170 | 1397 | 910 | 0 | 1250 | 0 | 2000 | 0 | 6330 | 1397 | 0 | -1397 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 48798 | 831 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | 831 | 473 | 0 | -473 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 | 0 | 0 | 8862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8862 | 0 | -8862
| Number of sites serviced |  | 0 | 67304 | 2636 | 1251 | 2410 | 0 | 3926 | 0 | 7556 | 0 | 16528 | 1251 | 0 | -1251
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 1676 | 1350 | 542 | 576 | 0 | 600 | 0 | 600 | 0 | 3126 | 542 | 0 | -542 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 127 | 22 | 45.731 | 14 | 0 | 15 | 0 | 19 | 0 | 70 | 45.731 | 0 | -45.731 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 31480 | 3365 | 9816.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3365 | 9816.5 | 0 | -9816.5 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 95.7 | 26 | 80.75 | 10 | 0 | 10 | 0 | 20 | 0 | 66 | 80.75 | 0 | -80.75 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 98 | 19.5 | 20.31 | 15 | 0 | 20 | 0 | 35 | 0 | 89.5 | 20.31 | 0 | -20.31 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 28 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 28 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 | 600 | 50 | 11 | 120 | 0 | 300 | 0 | 600 | 0 | 1070 | 11 | 0 | -11 | TRUE
| Number of additional households to be provided with water connections | 0 | 58678 | 18500.99 | 4816 | 3044 | 300 | 0 | 600 | 0 | 1200 | 0 | 6916 | 3044 | 0 | -3044 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 | 2800 | 100 | 70 | 500 | 0 | 1600 | 0 | 2800 | 0 | 5000 | 70 | 0 | -70 | TRUE
| Number of additional households to be provided with sewer connections |  | 155564 | 15830.99 | 5236 | 3919 | 300 | 0 | 600 | 0 | 1200 | 0 | 7336 | 3919 | 0 | -3919 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 799510 | 799510 | 799564 | 797064 | 0 | 797064 | 0 | 797064 | 0 | 3190702 | 799564 | 0 | -799564 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 88 | 88 | 88 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 90 | 0 | -90 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 950437 | 950437 | 801407 | 164000 | 0 | 164000 | 0 | 164000 | 0 | 1442437 | 801407 | 0 | -801407
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 245198 | 39750 | 7500 | 3319 | 1000 | 0 | 2000 | 0 | 2000 | 0 | 12500 | 3319 | 0 | -3319 | TRUE
| Number of additional high mast lights installed |  | 0 | 85 | 0 | 0 | 20 | 0 | 30 | 0 | 30 | 0 | 80 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 | 1473252 | 364506 | 75841 | 0 | 0 | 0 | 0 | 0 | 0 | 364506 | 75841 | 0 | -75841 | TRUE
| Number of additional street lights installed |  | 0 | 600 | 225 | 70 | 100 | 0 | 200 | 0 | 200 | 0 | 725 | 70 | 0 | -70 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 7 | 2 | 1 | 2 | 0 | 2 | 0 | 3 | 0 | 9 | 1 | 0 | -1 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 | 15 | 1 | 1 | 1 | 0 | 2 | 0 | 8 | 0 | 12 | 1 | 0 | -1 | TRUE
| Number of clinics to be developed / upgraded |  | 0 | 6 | 2 | 2 | 1 | 0 | 1 | 0 | 2 | 0 | 6 | 2 | 0 | -2 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 4 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 5 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 12 | 1 | 1 | 1 | 0 | 2 | 0 | 1 | 0 | 5 | 1 | 0 | -1 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 7996 | 83205 | 16001 | 15929 | 31500 | 0 | 33750 | 0 | 9000 | 0 | 90251 | 15929 | 0 | -15929 | TRUE
TRUE
BUF

## BUF
BUF - Buffalo City
Statistical indicators on service delivery as at the beginning of 2016/17 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements |  | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity |  | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services |  | Households
|  | Number of households living in informal areas receiving water services |  | Households
|  | Number of households in formal areas receiving sewerage services |  | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) |  | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2016/17
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2016/17 | Target for 2016/17 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2016/17. | Actual output for 2016/17 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 | 48664 | 700 | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 339 | 0 | -339 | TRUE
| Percentage density reduction in total informal settlements |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 |  | 48664 | 700 | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 339 | 0 | -339 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 | 48446 | 1000 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 370 | 0 | -370
| Number of Title deeds transferred to eligible beneficiaries |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 25 | 3 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5.1 | 0 | -5.1 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 120 | 15 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9.5 | 0 | -9.5 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 3 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 99% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 | 99% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 | Completion of phase 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 1200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 0 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 |  | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 | 3 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 7996 | 7996 | 1999 | 1623 |  | 0 | 0 | 0 | 0 | 0 | 1999 | 1623 | 0 | -1623 | TRUE
TRUE
BUF

## NMA
NMA - Nelson Mandela Bay
Statistical indicators on service delivery as at the beginning of 2016/17 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements | 30202 | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity | 276850 | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services | 276850 | Households
|  | Number of households living in informal areas receiving water services | 30202 | Households
|  | Number of households in formal areas receiving sewerage services | 276850 | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) | 90677 | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2016/17
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2016/17 | Target for 2016/17 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2016/17. | Actual output for 2016/17 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 | 120 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | -120 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Percentage density reduction in total informal settlements |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 | 4 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | -2 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 | 1200 | 300 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 186 | 0 | -186 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 4 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | -2 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 |  | 0 | 8862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8862 | 0 | -8862
| Number of sites serviced |  | 0 | 5655 | 566 | 546 | 0 | 0 | 0 | 0 | 0 | 0 | 566 | 546 | 0 | -546
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 7, 000 | 1000 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 90 | 0 | -90 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 30000 | 3000 | 9349 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 9349 | 0 | -9349 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 3000 | 1256 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 1256 | 119 | 0 | -119 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 | 3000 | 1256 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 1256 | 119 | 0 | -119 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  |  | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | -2 | TRUE
| Number of households living in informal areas with solid waste removal service |  |  | 0 |  | 14968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14968 | 0 | -14968
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | -93 | TRUE
| Number of additional high mast lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  |  | 0 |  | 75841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75841 | 0 | -75841 | TRUE
| Number of additional street lights installed |  | 0 | 0 | 125 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 70 | 0 | -70 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 | 6009 | 1402 | 1496 | 0 | 0 | 0 | 0 | 0 | 0 | 1402 | 1496 | 0 | -1496 | TRUE
|  |  | 1: 0; 2: 1830; 3: 270; 4: 339 | TRUE
NMA

## MAN
MAN - Mangaung
Statistical indicators on service delivery as at the beginning of 2016/17 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements |  | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity |  | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services |  | Households
|  | Number of households living in informal areas receiving water services |  | Households
|  | Number of households in formal areas receiving sewerage services |  | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) |  | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2016/17
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2016/17 | Target for 2016/17 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2016/17. | Actual output for 2016/17 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Percentage density reduction in total informal settlements |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
TRUE
MAN

## EKU
EKU - Ekurhuleni Metro
Statistical indicators on service delivery as at the beginning of 2016/17 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service | 834712 | Sites
|  | Number of households living in informal settlements | 164000 | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity | 834712 | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services | 986.279 | Households
|  | Number of households living in informal areas receiving water services | 164000 | Households
|  | Number of households in formal areas receiving sewerage services | 985.876 | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) | 797064 | Households
|  | Number of households living in informal areas with access to refuse removal | 164000 | Households
QUARTERLY PERFORMANCE REPORTS - 2016/17
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2016/17 | Target for 2016/17 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2016/17. | Actual output for 2016/17 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Per centage density reduction in total informal settlements |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 | 8 | 1 | 0 | 2 | 0 | 2 | 0 | 3 | 0 | 8 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 | 4551 | 0 | 0 | 1000 | 0 | 1551 | 0 | 2000 | 0 | 4551 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 976 | 200 | 265 | 376 | 0 | 300 | 0 | 100 | 0 | 976 | 265 | 0 | -265 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 67 | 19 | 21 | 14 | 0 | 15 | 0 | 19 | 0 | 67 | 21 | 0 | -21 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 1300 | 350 | 434 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 434 | 0 | -434 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 64 | 24 | 69 | 10 | 0 | 10 | 0 | 20 | 0 | 64 | 69 | 0 | -69 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 15 | 2 | 0 | 5 | 0 | 10 | 0 | 15 | 0 | 32 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 1200 | 100 |  | 300 | 0 | 600 | 0 | 1200 | 0 | 2200 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 | 1200 | 100 |  | 300 | 0 | 600 | 0 | 1200 | 0 | 2200 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 797064 | 797064 | 797064 | 797064 | 0 | 797064 | 0 | 797064 | 0 | 3188256 | 797064 | 0 | -797064 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 164000 | 164000 |  | 164000 | 0 | 164000 | 0 | 164000 | 0 | 656000 | 0 | 0 | 0
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 6000 | 1000 | 12 | 1000 | 0 | 2000 | 0 | 2000 | 0 | 6000 | 12 | 0 | -12 | TRUE
| Number of additional high mast lights installed |  | 0 | 80 | 0 | 0 | 20 | 0 | 30 | 0 | 30 | 0 | 80 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 | 600 | 100 | 0 | 100 | 0 | 200 | 0 | 200 | 0 | 600 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 | 5 | 1 | 1 | 1 | 0 | 2 | 0 | 1 | 0 | 5 | 1 | 0 | -1 | TRUE
| Number of clinics to be developed / upgraded |  | 0 | 6 | 2 | 2 | 1 | 0 | 1 | 0 | 2 | 0 | 6 | 2 | 0 | -2 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 | 1 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 5 | 1 | 1 | 1 | 0 | 2 | 0 | 1 | 0 | 5 | 1 | 0 | -1 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 | 18000 | 0 | 0 | 9000 | 0 | 0 | 0 | 9000 | 0 | 18000 | 0 | 0 | 0 | TRUE
TRUE
EKU

## JHB
JHB - City Of Johannesburg
Statistical indicators on service delivery as at the beginning of 2016/17 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements |  | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity |  | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services |  | Households
|  | Number of households living in informal areas receiving water services |  | Households
|  | Number of households in formal areas receiving sewerage services |  | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) |  | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2016/17
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2016/17 | Target for 2016/17 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2016/17. | Actual output for 2016/17 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Percentage density reduction in total informal settlements |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
TRUE
JHB

## TSH
TSH - City Of Tshwane
Statistical indicators on service delivery as at the beginning of 2016/17 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements | 186862 | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity | 733230 | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services | 740202 | Households
|  | Number of households living in informal areas receiving water services | 186862 | Households
|  | Number of households in formal areas receiving sewerage services | 716277 | Households
|  | Number of households living in informal areas receiving sewerage services | 186862 | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) | 2446 | Households
|  | Number of households living in informal areas with access to refuse removal | 186862 | Households
QUARTERLY PERFORMANCE REPORTS - 2016/17
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2016/17 | Target for 2016/17 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2016/17. | Actual output for 2016/17 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Percentage density reduction in total informal settlements |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 130 | 130 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 132 | 0 | -132 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Annual Target
| Number of households living in informal backyard rental agreement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 25 |  | 17.391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.391 | 0 | -17.391 | TRUE | No target for Q1
| KMs of new gravelled roads to be built | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 19.7 | 2 | 11.75 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11.75 | 0 | -11.75 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 4800 | 960 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 900 | 0 | -900 | TRUE | Our indicator is : Number of households with a full water connection
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 | 130 | 130 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 132 | 0 | -132 | TRUE | We measure informal settlements not households
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 2446 | 2446 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2446 | 2500 | 0 | -2500 | TRUE | Nr of areas provided with weekly minimal waste removal services.
| Number of waste minimisation projects initiated/ upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 130 | 130 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 132 | 0 | -132 |  | We measure number of informal settlements provided with weekly minimal waste removal services not households
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 2550 | 500 | 458 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 458 | 0 | -458 | TRUE | Nr on new electricity connections provided
| Number of additional high mast lights installed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | Nr of recreational facilities upgraded. This is an annual target
| Number of parks / leisure facilities to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | This is a project. Tender documentation submitted for BSC consideration and advertising of the Tender. Bill of Quantities for the refurbishment of Rayton CLinic has been re-submitted for Bid Specification Committee consideration on the 05th September 2016.
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | This is an annual target
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | Priorities revisited for the financial year as tenders EMS03/04/08: 2015/16 are not yet approved. In process to appoint a consultant from an approved list of consultants at SCM to address new priorities. Targets achieved to date. In process to review cash flow for purchasing of new hardware due to changed approach
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
TRUE
TSH

## ETH
ETH - eThekwini
Statistical indicators on service delivery as at the beginning of 2016/17 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service | 742 | Sites
|  | Number of households living in informal settlements | 245699 | Households
|  | Number of hectares of land already acquired and suitable for human settlements development | 50 | hectares
|  | Number of households in formal areas with access to basic electricity | 0 | Households
|  | Number of households living in informal areas with access to basic electricity | 0 | Households
|  | Number of households in formal areas receiving water services | 0 | Households
|  | Number of households living in informal areas receiving water services | 0 | Households
|  | Number of households in formal areas receiving sewerage services | 285379 | Households
|  | Number of households living in informal areas receiving sewerage services | 117062 | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) | 370812 | Households
|  | Number of households living in informal areas with access to refuse removal | 272098 | Households
QUARTERLY PERFORMANCE REPORTS - 2016/17
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2016/17 | Target for 2016/17 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2016/17. | Actual output for 2016/17 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 | 150 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 |  | 20-60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Percentage density reduction in total informal settlements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 | 5000 | 1350 | 1094 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 1094 | 0 | -1094 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 | 34 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  |  | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 | 3096 | 320 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 335 | 0 | -335
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 200 | 50 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 75 | 0 | -75 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 10 | 0 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | -2.24 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 25 | 2 | 5.31 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5.31 | 0 | -5.31 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 28 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 28 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 58678 | 12500 | 2500 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2025 | 0 | -2025 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 155564 | 11500 | 3750 | 3668 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 3668 | 0 | -3668 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 88 | 88 | 88 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 88 | 0 | -88 | TRUE
| Number of households living in informal areas with solid waste removal service |  |  | 786307 | 786307 | 786307 | 0 | 0 | 0 | 0 | 0 | 0 | 786307 | 786307 | 0 | -786307
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 245198 | 30000 | 6000 | 2756 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 2756 | 0 | -2756 | TRUE
| Number of additional high mast lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 | 1473252 | 364506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364506 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 | 6200 | 1350 | 587 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 587 | 0 | -587 | TRUE
TRUE
ETH

## CPT
CPT - Cape Town
Statistical indicators on service delivery as at the beginning of 2016/17 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements |  | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity |  | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services |  | Households
|  | Number of households living in informal areas receiving water services |  | Households
|  | Number of households in formal areas receiving sewerage services |  | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) |  | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2016/17
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2016/17 | Target for 2016/17 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2016/17. | Actual output for 2016/17 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 | 45 | 45 | 45 | 45 |  | 45 |  | 45 | 0 | 180 | 45 | 0 | -45 | TRUE
| Percentage density reduction in total informal settlements |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 | 2000 | 520 | 117 | 910 |  | 1250 |  | 2000 | 0 | 4680 | 117 | 0 | -117 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 1: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0
| Number of households living in informal backyard rental agreement |  | 1: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0
| Number of sites serviced |  | 0 | 5556 | 750 |  | 1410 |  | 2375 |  | 5556 |  | 10091 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 500 | 100 | 112 | 200 | 0 | 300 | 0 | 500 | 0 | 1100 | 112 | 0 | -112 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 60 |  | 24 |  | 0 |  | 0 |  | 0 | 0 | 24 | 0 | -24 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 12 |  | 0 |  | 0 |  | 0 | Annual Target | 0 | Invalid Input | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 55 | 15 | 15 | 10 | 0 | 10 | 0 | 20 | 0 | 55 | 15 | 0 | -15 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 | 600 | 50 | 11 | 120 | 0 | 300 | 0 | 600 | 0 | 1070 | 11 | 0 | -11 | TRUE
| Number of additional households to be provided with water connections | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 | 2800 | 100 | 70 | 500 | 0 | 1600 | 0 | 2800 | 0 | 5000 | 70 | 0 | -70 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 2 | 2 | 1 | 2 | 0 | 2 | 0 | 2 | 0 | 8 | 1 | 0 | -1 | TRUE | Comment: Refers to sportsfield upgrades. 2 Synthetic Pitches: 1. Hanover Park - The contractor's dismal performance is still ongoing. the Engineer has issued a breach notice for the contractor to rectify the existing poor performance breach within 14 day. The contractor has failed to comply with the Engineer's breach notice. . 2. Atlantis The project is complete and handed back to the City. 12 Month maintenance period is currently applicable and will end on 22 September 2017 | Line department is busy preparing for termination
| Number of parks / leisure facilities to be developed / upgraded |  | 0 | 7 | 0 | 0 | 0 |  | 0 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | TRUE | Comment: Refers to park upgrades. 1. Upgrade of Sea Point Promenade R4m 2. Upgrade Atlantis Smart Park R8m 3. Upgrade - Manenberg Integrated Project R5m 4. East: Khayelitsha Wetlands Park Upgrade R1,5m 5. Macassar POS system development R1m 6. Upgrade Park - Seawinds: Smart Park R4m 7. Upgrade Park NY10 R1m
| Number of clinics to be developed / upgraded |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | Nantes ECD completed slightly ahead of schedule. | None required
| Number of community swimming pools to be developed / upgraded |  | 0 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 0 | 1 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | Comment: Eikendal upgrade, Q4 reporting
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 | 4 | 0 | 0 | 0 |  | 0 |  | 4 | 0 | 4 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | Comment: Refers to upgrades, Q4 1. Maitland Cemetery Upgrade Roads & Infras R2m 2. North: Maitland Crematorium & Chapel Upgrade R2,5m 3. Upgrade of Rusthof Cemetery R1.5m 4. East: Welmoed Cemetery R1m
| Number of abbattoirs to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 | 45000 | 11250 | 12223 | 22500 | 0 | 33750 | 0 | 0 | 0 | 67500 | 12223 | 0 | -12223 | TRUE | 973 (8.6%) work opportunities ahead of schedule. | None required
TRUE
CPT