## Summary
Consolidated information for all metros
Statistical indicators on service delivery as at the beginning of 2018/19 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service | 752775 | Sites
|  | Number of households living in informal settlements | 165235 | Households
|  | Number of hectares of land already acquired and suitable for human settlements development | 80 | hectares
|  | Number of households in formal areas with access to basic electricity | 1797937 | Households
|  | Number of households living in informal areas with access to basic electricity | 131380 | Households
|  | Number of households in formal areas receiving water services | 2071890 | Households
|  | Number of households living in informal areas receiving water services | 209163 | Households
|  | Number of households in formal areas receiving sewerage services | 1347318 | Households
|  | Number of households living in informal areas receiving sewerage services | 169695 | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) | 1190855 | Households
|  | Number of households living in informal areas with access to refuse removal | 165105 | Households
QUARTERLY PERFORMANCE REPORTS - 2018/19
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2018/19 | Target for 2018/19 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2018/19. | Actual output for 2018/19 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Percentage density reduction in total informal settlements |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 154 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 40365 | 3235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 140 | 134 | 134 | 134 | 0 | 134 | 0 | 134 | 0 | 536 | 134 | 0 | -134 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 866 | 2200 | 375 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 21 | 0 | -21
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 4000 | 200 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 256 | 0 | -256 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 12 | 15.5 | 5.12 | 1.2 | 0 | 0 | 0 | 0 | 1.5 | 0 | 6.62 | 1.2 | 0 | -1.2 | TRUE
| KMs of new gravelled roads to be built | 0 | 25 | 5 | 8.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.67 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 105 | 170 | 105.42 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 105.42 | 8 | 0 | -8 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 1.5 | 36.2 | 1.57 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 33.57 | 1 | 0 | -1 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 30 | 35 | 4.4 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 5.5 | 0 | -5.5 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 31857 | 8704 | 1940 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 1940 | 41 | 0 | -41 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 12617 | 2700 | 1579 | 2500 | 0 | 2200 | 0 | 5217 | 0 | 12617 | 1579 | 0 | -1579 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 114394 | 7434 | 2120 | 1655 | 0 | 0 | 0 | 0 | 0 | 0 | 2120 | 1655 | 0 | -1655 | TRUE
| Number of additional households to be provided with sewer connections |  | 536 | 4040 | 0 | 0 | 50 | 0 | 250 | 0 | 3740 | 0 | 4040 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 871285 | 1850 | 1990 | 100 | 0 | 100 | 0 | 100 | 0 | 2150 | 1990 | 0 | -1990 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 | 12 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | -2 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 10134 | 3134 | 3833 | 134 | 0 | 134 | 0 | 134 | 0 | 3536 | 3833 | 0 | -3833
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 400 | 3180 | 300 | 390 | 400 | 0 | 400 | 0 | 500 | 0 | 1600 | 390 | 0 | -390 | TRUE
| Number of additional high mast lights installed |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 | 1500 | 12876 | 12650 | 0 | 0 | 0 | 0 | 0 | 0 | 12876 | 12650 | 0 | -12650 | TRUE
| Number of additional street lights installed |  | 100 | 7250 | 700 | 1819 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1819 | 0 | -1819 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | -2 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | -1 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 5360 | 64565 | 13875 | 11464 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 11464 | 0 | -11464 | TRUE
TRUE
BUF

## BUF
BUF - Buffalo City
Statistical indicators on service delivery as at the beginning of 2018/19 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service | 0 | Sites
|  | Number of households living in informal settlements |  | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity |  | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services | 128260 | Households
|  | Number of households living in informal areas receiving water services | 43928 | Households
|  | Number of households in formal areas receiving sewerage services | 154125 | Households
|  | Number of households living in informal areas receiving sewerage services | 4590 | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) |  | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2018/19
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2018/19 | Target for 2018/19 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2018/19. | Actual output for 2018/19 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Per centage density reduction in total informal settlements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 40365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
TRUE
BUF

## NMA
NMA - Nelson Mandela Bay
Statistical indicators on service delivery as at the beginning of 2018/19 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements |  | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity |  | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services |  | Households
|  | Number of households living in informal areas receiving water services |  | Households
|  | Number of households in formal areas receiving sewerage services |  | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) |  | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2018/19
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2018/19 | Target for 2018/19 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2018/19. | Actual output for 2018/19 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Per centage density reduction in total informal settlements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
TRUE
NMA

## MAN
MAN - Mangaung
Statistical indicators on service delivery as at the beginning of 2018/19 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements |  | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity |  | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services |  | Households
|  | Number of households living in informal areas receiving water services |  | Households
|  | Number of households in formal areas receiving sewerage services |  | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) |  | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2018/19
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2018/19 | Target for 2018/19 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2018/19. | Actual output for 2018/19 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Per centage density reduction in total informal settlements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
TRUE
MAN

## EKU
EKU - Ekurhuleni Metro
Statistical indicators on service delivery as at the beginning of 2018/19 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements |  | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity |  | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services |  | Households
|  | Number of households living in informal areas receiving water services |  | Households
|  | Number of households in formal areas receiving sewerage services |  | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) |  | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2018/19
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2018/19 | Target for 2018/19 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2018/19. | Actual output for 2018/19 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Per centage density reduction in total informal settlements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
TRUE
EKU

## JHB
JHB - City Of Johannesburg
Statistical indicators on service delivery as at the beginning of 2018/19 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements |  | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity |  | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services |  | Households
|  | Number of households living in informal areas receiving water services |  | Households
|  | Number of households in formal areas receiving sewerage services |  | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) |  | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2018/19
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2018/19 | Target for 2018/19 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2018/19. | Actual output for 2018/19 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Per centage density reduction in total informal settlements |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 | 200 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 2000 | 200 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 256 | 0 | -256 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 12 | 2 | 3.92 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.92 | 0 | 0 | 0 | TRUE
| KMs of new gravelled roads to be built | 0 | 25 | 5 | 8.67 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8.67 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 105 | 35 | 100.42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100.42 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 1.5 | 0.2 | 0.57 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.57 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 30 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 31857 | 8004 | 1840 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 113899 | 4834 | 1620 | 469 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 469 | 0 | -469 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 864185 | 869 082 | 869 082 | 0 | 0 | 0 | 0 | 0 | 0 | Invalid Input | Invalid Input | 0 | Invalid Input | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 | 10 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | -2 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 183 895 | 183 895 | 183 895 | 0 | 0 | 0 | 0 | 0 | 0 | Invalid Input | Invalid Input | 0 | Invalid Input
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 1580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 0 | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 |  | 12501 | 12501 | 0 | 0 | 0 | 0 | 0 | 0 | 12501 | 12501 | 0 | -12501 | TRUE
| Number of additional street lights installed |  | 0 | 2000 | 100 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 189 | 0 | -189 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 |  | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | -2 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | -1 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 5360 | 29065 | 5000 | 2529 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2529 | 0 | -2529 | TRUE
TRUE
JHB

## TSH
TSH - City Of Tshwane
Statistical indicators on service delivery as at the beginning of 2018/19 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service | 752775 | Sites
|  | Number of households living in informal settlements | 130 | Households
|  | Number of hectares of land already acquired and suitable for human settlements development | 0 | hectares
|  | Number of households in formal areas with access to basic electricity | 747208 | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services | 752775 | Households
|  | Number of households living in informal areas receiving water services | 130 | Households
|  | Number of households in formal areas receiving sewerage services | 2338 | Households
|  | Number of households living in informal areas receiving sewerage services | 0 | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) | 0 | Households
|  | Number of households living in informal areas with access to refuse removal | 0 | Households
QUARTERLY PERFORMANCE REPORTS - 2018/19
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2018/19 | Target for 2018/19 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2018/19. | Actual output for 2018/19 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Per centage density reduction in total informal settlements |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 134 | 134 | 134 | 134 |  | 134 | 0 | 134 | 0 | 536 | 134 | 0 | -134 | TRUE | Formulae used to calculate this indicator is an average not sum as per the spreadsheet. Annual Target is 134
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 |  | Annual Target
| Number of households living in informal backyard rental agreement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 1.5 | 0 | 0 | 0 |  | 0 |  | 1.5 | 0 | 1.5 | 0 | 0 | 0 | TRUE | A nnual targert is 1.5 not 2
| KMs of new gravelled roads to be built | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 32 | 0 | 0 | 0 |  | 0 |  | 32 | 0 | 32 | 0 | 0 | 0 | TRUE | Annual Target
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 12617 | 2700 | 1579 | 2500 |  | 2200 |  | 5217 | 0 | 12617 | 1579 | 0 | -1579 | TRUE | This is two targets combined (Water and Sanitation Department and Housing and Human Settlement department). Reason for Variance is that the KPI is dependent on connection applications received from consumers. The Contract for the installation of water meters ended on the 31st of August 2018
| 2 |  | 1: 0 | TRUE
Sewerage |  |  | 1: 0 | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 | 4040 | 0 |  | 50 |  | 250 |  | 3740 |  | 4040 | 0 | 0 | 0 | TRUE | Water and Sanitation Dept. Progress: Atteridgeville x19 Sewer Project: 95% of pipe installation and CCTV testing. Foundation of a pump station, concrete chamber is 70% complete. Housing and Human Settlement Progress : Progress thus far:Excavation, bedding, pipe laying, blanket and backfilling
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 100 | 100 | 100 | 100 |  | 100 |  | 100 | 0 | 400 | 100 | 0 | -100 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 1: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 134 | 134 | 134 | 134 |  | 134 |  | 134 | 0 | 536 | 134 | 0 | -134
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 1600 | 300 | 390 | 400 |  | 400 |  | 500 | 0 | 1600 | 390 | 0 | -390 | TRUE | The KPI is dependent on connection applications received from consumers. Demand was slightly higher for the quarter.
| Number of additional high mast lights installed |  | 1: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 1: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of additional street lights installed |  | 1: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE | UPGRADE OF CALEDONIAN STADIUM. Planned Milestone : Procurement of contractor. Negotiations with previous contractor resolved. Reports to rescind previous resolution to serve and be approved during October 2018. Milestone not achieved, Project put on hold until outstanding legal matters resolved. Mitigation Plan : Reports to Council to rescind previous Urban Park resolution. Approval by end October 2018. Tender process to appoint contractor to commence in November 2018. UPGRADE OF REFILWE STADIUM. Planned Milestone : Procurement of contractor, Tender closed, adjudication completed and approved by BAC. Appointment letter awaited.
| Number of parks / leisure facilities to be developed / upgraded |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of clinics to be developed / upgraded |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE | REPLACEMENT OF RAYTON CLINIC : Planned Milestone : Complete the roof cover, plastering, painting, glazing, installing ceiling, tiling, install doors, electrical, electronics and mechanical works. Project overall percentage - 60%. EXTENSION OF ROSSLYN CLINIC : Planned Milestone : Finalise professional work. Concept stage, overall percentage 100%. All professional planning work has been submitted - 100%. NEW CLINIC LUSAKA : Planned Milestone : Finalise professional work. Concept stage, overall percentage 100%. All professional planning work has been submitted - 100%
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of markets to be developed / upgraded |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 1: 0; 6: 0; 8: 0; 10: 0; [3 + 5 + 7 + 9] 11: 0; [4+6+8+10] 12: 0; [4+6+8+10] 13: 0; [13-12] 14: 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TRUE
TRUE
TSH

## ETH
ETH - eThekwini
Statistical indicators on service delivery as at the beginning of 2018/19 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements |  | Households
|  | Number of hectares of land already acquired and suitable for human settlements development |  | hectares
|  | Number of households in formal areas with access to basic electricity |  | Households
|  | Number of households living in informal areas with access to basic electricity |  | Households
|  | Number of households in formal areas receiving water services |  | Households
|  | Number of households living in informal areas receiving water services |  | Households
|  | Number of households in formal areas receiving sewerage services |  | Households
|  | Number of households living in informal areas receiving sewerage services |  | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) |  | Households
|  | Number of households living in informal areas with access to refuse removal |  | Households
QUARTERLY PERFORMANCE REPORTS - 2018/19
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2018/19 | Target for 2018/19 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2018/19. | Actual output for 2018/19 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Per centage density reduction in total informal settlements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional street lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
TRUE
ETH

## CPT
CPT - Cape Town
Statistical indicators on service delivery as at the beginning of 2018/19 (to be completed only at the beginning of the municipal financial year)
Current status
|  | Number of sites currently serviced with electricity, water (house connection), sewerage removal service and solid waste removal service |  | Sites
|  | Number of households living in informal settlements | 165105 | Households
|  | Number of hectares of land already acquired and suitable for human settlements development | 80 | hectares
|  | Number of households in formal areas with access to basic electricity | 1050729 | Households
|  | Number of households living in informal areas with access to basic electricity | 131380 | Households
|  | Number of households in formal areas receiving water services | 1190855 | Households
|  | Number of households living in informal areas receiving water services | 165105 | Households
|  | Number of households in formal areas receiving sewerage services | 1190855 | Households
|  | Number of households living in informal areas receiving sewerage services | 165105 | Households
|  | Number of households in formal areas with kerb-side refuse removal services (once a week) | 1190855 | Households
|  | Number of households living in informal areas with access to refuse removal | 165105 | Households
QUARTERLY PERFORMANCE REPORTS - 2018/19
Programme / Subprogramme / Performance Measures |  |  | Backlog as at beginning of 2018/19 | Target for 2018/19 as per the SDBIP | 1st Quarter Planned output as per SDBIP | 1st Quarter Actual output | 2nd Quarter Planned output as per SDBIP | 2nd Quarter Actual output | 3rd Quarter Planned output as per SDBIP | 3rd Quarter Actual output | 4th Quarter Planned output as per SDBIP | 4th Quarter Actual output | Summary of Planned output as per SDBIP | Summary of Actual output for 2018/19. | Actual output for 2018/19 as per Annual Report | Variation |  | Reason(s) for variation | Remedial action
[13 empty] | [3 + 5 + 7 + 9] | [4+6+8+10] |  | [13-12]
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
QUARTERLY OUTPUTS
Spatial Development and the Built Environment:
| Number of hectares of land procured and suitable for Greenfields development | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land procured and suitable for Brownfield development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of hectares of land proclaimed (township establishment completed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of dwelling units developed per hectare | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Per centage density reduction in total informal settlements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading | 0 | 0 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal settlements targeted for upgrading |  | 0 | 3235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for upgrading with upgrading plans |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of informal settlements upgraded (services provided): In Situ | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of informal settlements targeted for formalisation (services provided): Relocated | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of households living in informal backyard rental agreement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of sites serviced |  | 0 | 2000 | 325 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 21 | 0 | -21
| Number of Title deeds transferred to eligible beneficiaries |  | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 13 | [15 empty] | TRUE
Roads and storm water: | [16 empty] | TRUE
TRUE
| KMs of new paved roads to be built | 0 | 0 | 12 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 1.2 | 0 | -1.2 | TRUE
| KMs of new gravelled roads to be built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| KMs of roads resurfaced/rehabilitated/resealed | 0 | 0 | 135 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | -8 | TRUE
| KMs of storm water drainage installed in addition to current ones | 0 | 0 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | -1 | TRUE
Transport:
| KMs of new pedestrian walkways to be constructed | 0 | 0 | 30 | 4.4 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 5.5 | 0 | -5.5 | TRUE
| Number of new bus terminals or taxi ranks to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of new bus/taxi stops to be constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 7 | [15 empty] | TRUE
Access to Services:
Water | [16 empty] | TRUE
| Number of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 | 700 | 100 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 41 | 0 | -41 | TRUE
| Number of additional households to be provided with water connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Sewerage | [16 empty] | TRUE
| Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers |  | 0 | 2600 | 500 | 1186 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1186 | 0 | -1186 | TRUE
| Number of additional households to be provided with sewer connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 2 | [15 empty] | TRUE
Solid Waste Management | [16 empty] | TRUE
| Number of additional households provided with access to weekly refuse removal |  | 0 | 7000 | 1750 | 1890 | 0 | 0 | 0 | 0 | 0 | 0 | 1750 | 1890 | 0 | -1890 | TRUE
| Number of waste minimisation projects initiated/ upgraded |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of households living in informal areas with solid waste removal service |  | 0 | 10000 | 3000 | 3699 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3699 | 0 | -3699
| 2 | [15 empty] | TRUE
Electricity | [16 empty] | TRUE
| Number of additional households living in formal areas provided with electricity connections |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional high mast lights installed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of additional households provided with access to Free Basic Electricity |  | 0 | 1500 | 375 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 149 | 0 | -149 | TRUE
| Number of additional street lights installed |  | 0 | 5250 | 600 | 1630 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 1630 | 0 | -1630 | TRUE
Socio-Economic Amenities | [16 empty] | TRUE
| Number of community halls to be developed / upgraded |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of sports fields and stadia to be developed / upgraded |  | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of parks / leisure facilities to be developed / upgraded |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of clinics to be developed / upgraded |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of pre-schools / early childhood development centres to be developed / upgraded developed |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of community swimming pools to be developed / upgraded |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of libraries to be developed / upgradeddeveloped |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of museums / theatres and art galleries to be developed / upgraded |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of cemetries to be developed / upgraded |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of abbattoirs to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of markets to be developed / upgraded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Number of fire safety and emergency facilities to be developed / upgraded |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 12 | [15 empty] | TRUE
Local Economic Development and Job Creation: | [16 empty] | TRUE
| Number of additional jobs to be created using the Expanded Public Works Programme guidelines and other municipal programmes |  | 0 | 35500 | 8875 | 8935 | 0 | 0 | 0 | 0 | 0 | 0 | 8875 | 8935 | 0 | -8935 | TRUE
TRUE
CPT