## Slide 1: MSCOA ICF: Change Management and the role of the Provincial Treasury
Presented by National Treasury: Chief Directorate Local Government Budget Analysis | 22 June 2015

## Slide 2
High Level Planned Activities
Actual
Output & and Planned Activities Leading to 1 July 2017
In progress…
Completed
13 – 24 months
25 – 36 months
37 months and beyond…
July - Dec 2014
Jan - June 2015
July 15 – June 16
July 16 – June 17
1 July 2017……….
mSCOA Project Phase 4
GO LIVE
Communications and Change Mgt. Strategy development:
PT site visits
Other forum such as PAG & CFO Forum
1) Communications and Change Mgt. Strategy development
2) Engage on database adjustments
3) Support business processes
4) Communications and Change Management Strategy roll-out
5) Establish capability gaps throughout process
7) SCOA Technical Committee Integration
8) Scale-up interface with municipalities
6) Standardise practice for issuance of circulars
9) Develop and roll-out capacitation plan based on gaps identified
2) Engage on database adjustments
3) Support business processes
4) Communication and change management roll-out:
mSCOA ICF, PT engagements, CFO Forums, etc.
Develop and distribute mSCOA Chart
Develop and implement FAQ SQL Databse (Web based)
9 provincial sessions (2014) Demystifying SCOA
5) Establish capacity gaps
6) Standardise practice for issuance of circulars
7) SCOA Technical Committee Integration
8) Scale-up interface with municipalites
9)Develop and roll-out capacitation plan based on gaps identified
mSCOA Work Steam 4: Transition and Change

## Slide 3
High Level Planned Activities
Actual
Output & and Planned Activities Leading to 1 July 2017
In progress…
Completed
13 – 24 months
25 – 36 months
37 months and beyond…
July - Dec 2014
Jan - June 2015
July 15 – June 16
July 16 – June 17
1 July 2017……….
mSCOA Project Phase 4
GO LIVE
Communications and Change Mgt. Strategy development:
PT site visits
Other forum such as PAG & CFO Forum
1) Communications and Change Mgt. Strategy development
2) Engage on database adjustments
3) Support business processes
4) Communications and Change Management Strategy roll-out
5) Establish capability gaps throughout process
7) SCOA Technical Committee Integration
8) Scale-up interface with municipalities
6) Standardise practice for issuance of circulars
9) Develop and roll-out capacitation plan based on gaps identified
2) Engage on database adjustments
3) Support business processes
4) Communication and change management roll-out:
mSCOA ICF, PT engagements, CFO Forums, etc.
Develop and distribute mSCOA Chart
Develop and implement FAQ SQL Databse (Web based)
9 provincial sessions (2014) Demystifying SCOA
5) Establish capacity gaps
6) Standardise practice for issuance of circulars
7) SCOA Technical Committee Integration
8) Scale-up interface with municipalities
9)Develop and roll-out capacitation plan based on gaps identified
mSCOA Work Steam 4: Transition and Change

## Slide 4
CHANGE AND TRANSITION
Embedding change in your head, heart and hand

## Slide 5
CHANGE AND TRANSITION
Embedding change in your head, heart and hand
Project governance
Project team
Project planning and administration
Demystifying SCOA, 2 day non-accredited, FAQ
Risk registers and issue logs
Learning and knowledge management
Communication
Change management
Sustaining the change

## Slide 6
CHANGE AND TRANSITION
Provincial team:
Governance:
Steering com.
Key decisions
Risk management
Sustaining SCOA:
Oversight role
Templates
Self assessments
Implementation:
Project team
Change and Trans.
Learning & Knowledge
Enablement/ training
Risk management
Municipal team:
Implementation:
Project team, planning, preparation
Change and Trans.
Vendor appointment and management
Enablement/ training in municipality
Risk management
Sustaining SCOA:
Oversight role
Templates
Self assessments

## Slide 7
PROVINCIAL FEEDBACK
CRITERIA | RATING
Project governance | Partially implemented or considered
Project team | Identified but not appointed
Project planning/ admin | Needs attention
ICF and other forums | Well attended
List/ liaison with stakeholders | Lists compiled but not engage as yet
Risk registers | Needs attention
FAQ database | To be communicated and monitored
Training participation | Well attended, asked for more
Change management | Only started

## Slide 8
WORKSHOPS
Three presentations:
Change management
Knowledge management
Vision and business case
Three workshop groups:
Vision, core message and business case
Knowledge management
Engagement plan

## Slide 9: 1. Review previous self-assessment 2. Review specific risks/ issues raised to date 3. Review progress to date, assist as required 4. Communication slides: Engaging and enabling the organisation 5. New self assessment
AGENDA FOR PROVINCIAL VISITS

## Slide 10
Questions