## Slide 1
Presentation to mSCOA GRAP Workshop
Hannes Dednam – Budget Office
EKURHULENI’S MODEL TO IMPLEMENT SCOA

## Slide 2: BACKGROUND
EMM - a pilot metro.
When did EMM start
How did we get approval of CM and Councilors
Start to identify new votes on SCOA
One-on-one approach
Dedicated official for SCOA

## Slide 3: BACKGROUND
What did we do ?
  Get a core team - Dedicated employees on project
  Service Provider
  Regular meetings
  Ensure ICT network stability
  Test system before going live.

## Slide 4: WHAT HAPPENED DURING / AFTER IMPLEMENTATION
  Inform departments of new vote structure (Video’s)
Correct wrong votes
Making sure all systems are integrating to new vote structure
Change Management report
Started with “As Is” business processes
Default codes in segments
Lost of momentum of project

## Slide 5: WHAT IS PLANS FOR 2016/17
Refinement of votes
  Number of votes are wrong
  Various segments must be completed – currently default numbers
Change Management – involve other departments
New budget on SCOA structure
Upload and testing on NT database

## Slide 6: WHAT IS PLANS FOR 2016/17
Work on business processes
Incorporate financial information of Entities
Upgrading of the financial system
Improve on Management Reports
Prepare new budget with refined votes

## Slide 7: CHALLENGES
Limited resources
Must do proper Change management
Review business processes (position papers by NT)
Reporting format

## Slide 8: CHALLENGES
Auditor-General involvement and understanding
Training
Comparative information
Changes on mSCOA versions
What is compliance

## Slide 9: CONCLUSION
Did EMM had a model??
Advise to other municipalities
  Start immediately – 01 July 2017
  Get people with commitment
  Be proud of mSCOA
  Do it right the first time
  Change Management important
  Identify Risk

## Slide 10: THANK YOU